ESA PSS-05-0 Issue 2

February 1991

E S A

S O F T W A R E

E N G I N E E R I N G

S T A N D A R D S

ISSUE 2

Prepared by:

ESA Board for Software

Standardisation and Control

(BSSC)

Approved by:

The Inspector General, ESA

European Space Agency/ Agence spatiale europeenne

8-10, rue Mario-Nikis, 75738 PARIS CEDEX, France

DCC - PUC

DOCUMENT STATUS SHEET

| DOCUMENT STATUS SHEET |  |  |  |
| --- | --- | --- | --- |
| 1. DOCUMENT TITLE: ESA PSS-05-0 Software Engineering Standards |  |  |  |
| 2. ISSUE | 3. REVISION | 4. DATE | 5. REASON FOR CHANGE |
| 0 1 | 0 0 | 1984 1987 | First issue of BSSC(84)1, Issue no 1 First issue of ESA PSS-05-0, Issue 1 |

Approved, 30th January 1991

Board for Software Standardisation and Control

C. Mazza, Chairman

Approved, 21st February 1991

Telematics Supervisory Board

Published by ESA Publications Division,

ESTEC, Noordwijk, The Netherlands.

Printed in the Netherlands.

ESA price code: E2

ISSN 0379 - 4059

Copyright  1991 by European Space Agency

TABLA DE CONTENIDOS

INTRODUCTION	9

1         PURPOSE OF THE STANDARDS	9

2         STRUCTURE OF THE STANDARDS	9

3         CLASSES OF STANDARD PRACTICES	9

3.1       Mandatory practices	9

3.2       Recommended practices	9

3.3       Guideline practices	10

4         APPLYING THE STANDARDS	10

4.1       Factors in applying the Standards	10

4.2       Applying the Standards in a system development	10

4.3       Methods and tools	11

P a r t  1   P r o d u c t   S t a n d a r d s	12

CHAPTER 1: THE SOFTWARE LIFE CYCLE	12

1.1       INTRODUCTION	12

1.2       PHASES, ACTIVITIES AND MILESTONES	12

1.2.1     UR phase: user requirements definition	14

1.2.2     SR phase: software requirements definition	14

1.2.3     AD phase: architectural design	14

1.2.4     DD phase: detailed design and production	15

1.2.5     TR phase: transfer	15

1.2.6     OM phase: operations and maintenance	15

1.3       LIFE CYCLE APPROACHES	16

1.3.1     The waterfall approach	16

1.3.2     The incremental delivery approach	16

1.3.3     The evolutionary development approach	17

1.4       PROTOTYPING	17

1.5       HANDLING REQUIREMENTS CHANGE	18

CHAPTER 2: THE USER REQUIREMENTS DEFINITION PHASE	18

2.1       INTRODUCTION	18

2.2       INPUTS TO THE PHASE	19

2.3       ACTIVITIES	19

2.3.1     Capture of user requirements	19

2.3.2     Determination of operational environment	20

2.3.3     Specification of user requirements	20

2.3.4     Reviews	21

2.4       OUTPUTS FROM THE PHASE	21

2.4.1     User Requirements Document	21

2.4.2     Acceptance test plans	22

2.4.3     Project management plan for the SR phase	22

2.4.4     Configuration management plan for the SR phase	22

2.4.5     Verification and validation plan for the SR phase	22

2.4.6     Quality assurance plan for the SR phase	22

CHAPTER 3:    THE SOFTWARE REQUIREMENTS DEFINITION PHASE	23

3.1       INTRODUCTION	23

3.2       INPUTS TO THE PHASE	23

3.3       ACTIVITIES	23

3.3.1     Construction of the logical model	24

3.3.2     Specification of software requirements	24

3.3.3     Reviews	27

3.4       OUTPUTS FROM THE PHASE	27

3.4.1     Software Requirements Document	28

3.4.2     System test plans	28

3.4.3     Project management plan for the AD phase	28

3.4.4     Configuration management plan for the AD phase	29

3.4.5     Verification and validation plan for the AD phase	29

3.4.6     Quality assurance plan for the AD phase	29

CHAPTER 4:  THE ARCHITECTURAL DESIGN PHASE	29

4.1       INTRODUCTION	29

4.2       INPUTS TO THE PHASE	29

4.3       ACTIVITIES	30

4.3.1     Construction of the physical model	30

4.3.2     Specification of the architectural design	32

4.3.3     Selection of programming languages	33

4.3.4     Reviews	33

4.4       OUTPUTS FROM THE PHASE	33

4.4.1     Architectural Design Document	34

4.4.2     Integration test plans	34

4.4.3     Project management plan for the DD phase	34

4.4.4     Configuration management plan for the DD phase	34

4.4.5     Verification and validation plan for the DD phase	34

4.4.6     Quality assurance plan for the DD phase	35

CHAPTER 5:  THE DETAILED DESIGN AND PRODUCTION PHASE	35

5.1       INTRODUCTION	35

5.2       INPUTS TO THE PHASE	35

5.3       ACTIVITIES	36

5.3.1     Detailed design	36

5.3.2     Production	37

5.3.3     Reviews	39

5.4       OUTPUTS FROM THE PHASE	39

5.4.1     Code	40

5.4.2     Detailed Design Document	40

5.4.3     Software User Manual	40

5.4.4     Project management plan for the TR phase	41

5.4.5     Configuration management plan for the TR phase	41

5.4.6     Acceptance test specification	41

5.4.7     Quality assurance plan for the TR phase	41

CHAPTER 6:  THE TRANSFER PHASE	41

6.1       INTRODUCTION	41

6.2       INPUTS TO THE PHASE	42

6.3       ACTIVITIES	42

6.3.1     Installation	42

6.3.2     Acceptance tests	42

6.3.3     Provisional acceptance	42

6.4       OUTPUTS FROM THE PHASE	43

6.4.1     Statement of provisional acceptance	43

6.4.2     Provisionally accepted software system	43

6.4.3     Software Transfer Document	43

CHAPTER 7: THE OPERATIONS AND MAINTENANCE PHASE	43

7.1       INTRODUCTION	43

7.2       INPUTS TO THE PHASE	44

7.3       ACTIVITIES	44

7.3.1     Final Acceptance	44

7.3.2     Maintenance	44

7.4       OUTPUTS FROM THE PHASE	45

7.4.1     Statement of final acceptance	45

7.4.2     Project History Document	45

7.4.3     Finally accepted software system	46

P a r t  2  P r o c e d u r e  S t a n d a r d s	46

CHAPTER 1:  MANAGEMENT OF THE SOFTWARE LIFE CYCLE	47

1.1       INTRODUCTION	47

1.2       SOFTWARE PROJECT MANAGEMENT	47

1.3       SOFTWARE CONFIGURATION MANAGEMENT	47

1.4       SOFTWARE VERIFICATION AND VALIDATION	47

1.5       SOFTWARE QUALITY ASSURANCE	48

CHAPTER 2: SOFTWARE PROJECT MANAGEMENT	48

2.1       INTRODUCTION	48

2.2       ACTIVITIES	48

2.2.1     Organising the project	48

2.2.2     Leading the project	49

2.2.3     Risk management	49

2.2.4     Technical management	49

2.2.5     Planning, scheduling and budgeting the work	49

2.2.6     Reporting project progress	50

2.3       THE SOFTWARE PROJECT MANAGEMENT PLAN	50

2.4       EVOLUTION OF THE SPMP THROUGHOUT THE LIFE CYCLE	50

2.4.1     UR phase	51

2.4.2     SR phase	51

2.4.3     AD phase	51

2.4.4     DD phase	52

CHAPTER 3: SOFTWARE CONFIGURATION MANAGEMENT	52

3.1       INTRODUCTION	52

3.2       ACTIVITIES	52

3.2.1     Configuration identification	53

3.2.2     Configuration item storage	54

3.2.3     Configuration change control	54

3.2.4     Configuration status accounting	56

3.2.5     Release	57

3.3       THE SOFTWARE CONFIGURATION MANAGEMENT PLAN	57

3.4       EVOLUTION OF THE SCMP THROUGHOUT THE LIFE CYCLE	57

3.4.1     UR phase	58

3.4.2     SR phase	58

3.4.3     AD phase	58

3.4.4     DD phase	58

CHAPTER 4:  SOFTWARE VERIFICATION AND VALIDATION	58

4.2       ACTIVITIES	59

4.2.1     Reviews	59

4.2.2     Tracing	60

4.2.3     Formal proof	61

4.2.4     Testing	61

4.2.5     Auditing	62

4.3       THE SOFTWARE VERIFICATION AND VALIDATION PLAN	62

4.4       EVOLUTION OF THE SVVP THROUGHOUT THE LIFE CYCLE	62

4.4.1     UR phase	62

4.4.2     SR phase	63

4.4.3     AD phase	63

4.4.4     DD phase	63

CHAPTER 5:  SOFTWARE QUALITY ASSURANCE	64

5.1       INTRODUCTION	64

5.2       ACTIVITIES	64

5.2.1     Management	64

5.2.2     Documentation	65

5.2.3     Standards, practices, conventions and metrics	65

5.2.4     Reviews and audits	65

5.2.5     Testing activities	65

5.2.6     Problem reporting and corrective action	65

5.2.7     Tools, techniques and methods	65

5.2.8     Code and media control	65

5.2.9     Supplier control	66

5.3       THE SOFTWARE QUALITY ASSURANCE PLAN	66

5.4       EVOLUTION OF THE SQAP THROUGHOUT THE LIFE CYCLE	66

5.4.1     UR phase	66

5.4.2     SR phase	66

5.4.3     AD phase	67

5.4.4     DD phase	67

P a r t  3   A p p e n d i c e s	68

APPENDIX A: GLOSSARY	68

A.1       LIST OF TERMS	68

A.2       LIST OF ACRONYMS	72

APPENDIX B   SOFTWARE PROJECT DOCUMENTS	73

APPENDIX C    DOCUMENT TEMPLATES	74

APPENDIX C.1  URD table of contents	74

APPENDIX C.2  SRD table of contents	75

APPENDIX C.3  ADD table of contents	76

APPENDIX C.4  DDD table of contents	77

APPENDIX C.5  SUM table of contents	77

APPENDIX C.6  STD table of contents	78

APPENDIX C.7  PHD table of contents	79

APPENDIX C.8  SPMP table of contents	79

APPENDIX C.9  SCMP table of contents	80

APPENDIC C.10  SVVP table of contents	81

APPENDIX C.11   SQAP table of contents	83

APPENDIX D   SUMMARY OF MANDATORY PRACTICES	84

APPENDIX D.1    SOFTWARE LIFE CYCLE	84

APPENDIX D.2    UR PHASE	84

APPENDIX D.3    SR PHASE	85

APPENDIX D.4    AD PHASE	86

APPENDIX D.5    DD PHASE	87

APPENDIX D.6    TR PHASE	88

APPENDIX D.7    OM PHASE	88

APPENDIX D.8    SOFTWARE PROJECT MANAGEMENT	89

APPENDIX D.9    SOFTWARE CONFIGURATION MANAGEMENT	89

APPENDIX D.10   SOFTWARE VERIFICATION AND VALIDATION	91

APPENDIX D.11   SOFTWARE QUALITY ASSURANCE	92

APPENDIX E  FORM TEMPLATES	93

Figures	96

Apendix Index	97

FOREWORD

Software engineering is an evolving discipline, and many changes have occurred in the field since the last issue of the ESA PSS-05-0 Software Engineering Standards in January 1987. The BSSC started, therefore, a programme to update the Standards in 1989.  The opinions of users of the Standards were invited, software engineering methods were reviewed, and standards recently issued by other organisations were examined.

Estamos esperando a Yannis (el español...aun no llega)

In 1989, the BSSC called for users of the Standards to submit change proposals. Nearly 200 separate proposals were received and many of the points they raised have been incorporated in this new issue of the Standards.

The BSSC has started the development of lower-level documents, called `Guides', which will describe in detail how to implement the practices described in the Standards. The Guides will also discuss software engineering methods. The evelopment work on the Guides has required careful scrutiny of the Standards, nd some changes in them have been found to be needed.

The last issue of the Standards took into account the software engineering standards published by the Institute of Electrical and Electronics Engineers ( IEEE).  Most of these standards are recognised by the American National Standards Institute (ANSI).  This issue takes into account several new standards which have been published by the IEEE since the last issue.

The following BSSC members have contributed to the implementation of this issue: Carlo Mazza (chairman), Bryan Melton, Daniel De Pablo, Adriaan Scheffer and Richard Stevens.

The BSSC wishes to thank Jon Fairclough for his assistance in the evelopment of the Standards and the Guides.  The BSSC expresses its gratitude to ll those software engineers in ESA and in Industry who have contributed roposals for the improvement of the Standards.

Requests for clarifications, change proposals or any other comment ncerning these Standards should be addressed to either:

| BSSC/ESOC Secretariat | BSSC/ESTEC Secretariat |
| --- | --- |
| Attention of Mr C Mazza | Attention of Mr A Scheffer |
| ESOC | ESTEC |
| Robert-Bosch-Strasse 5 | Postbus 299 |
| D-6100 Darmstadt | NL-2200 AG Noordwijk |
| Germany | The Netherlands |

# INTRODUCTION

## 1         PURPOSE OF THE STANDARDS

This document describes the software engineering standards to be applied for all deliverable software implemented for the European   Space Agency (ESA), either in house or by industry.

Software is defined in these Standards as the programs,   procedures, rules and all associated documentation pertaining to the  operation of a computerised system. These Standards are concerned with all oftware aspects of a system, including its interfaces with the computer hardware nd with other components of the system.

Software may be either a subsystem of a more complex system or it may  be an independent system.

Where ESA PSS-01-series documents are applicable, and as a consequence ESA PSS-01-21, `Software Product Assurance Requirements for ESA space Systems' is also applicable, Part 2, Chapter 5 of these Standards, Software Quality Assurance', ceases to apply.

## 2         STRUCTURE OF THE STANDARDS

The ESA Software Engineering Standards are divided into three  parts:

Part 1, `Product Standards', contains standards, ecommendations and guidelines concerning the product, i.e. the software to be defined, implemented, operated and maintained.

Part 2, `Procedure Standards', describes the procedures which  are used to manage a software project.

Part 3, `Appendices', contains summaries, tables, forms and      checklists of mandatory practices.

## 3         CLASSES OF STANDARD PRACTICES

Three categories of standard practices are used in the ESA Software Engineering Standards: mandatory practices, recommended   practices and guidelines.

### 3.1       Mandatory practices

Sentences containing the word `shall' are mandatory practices.     These practices must be followed, without exception, in all software   projects. The word `must' is used in statements that repeat a   mandatory practice.

### 3.2       Recommended practices

Sentences containing the word `should' are strongly recommended practices. A justification to the appropriate level in the Agency's   hierarchy is needed if they are not followed.

### 3.3       Guideline practices

Sentences containing the word `may' are guidelines.  No  justification is required if they are not followed.

## 4         APPLYING THE STANDARDS

Software projects vary widely in purpose, size, complexity and     availability of resources.  Software project management should define  how the Standards are to be applied in the planning documents (see  Part 2). Deciding how standards are to be applied in specific projects is often alled `tailoring'.

### 4.1       Factors in applying the Standards

A number of factors can influence how the Standards are  applied, for example the:

- project cost, both in development and operation;

- number of people required to develop, operate and maintain the   software;

- number of potential users of the software;

- amount of software that has to be produced;

- criticality of the software, as measured by the consequences of   its failure;

- complexity of the software, as measured by the number of interfaces or a similar metric;

- completeness and stability of the user requirements;

- risk values included with the user requirements.

Note that two man years or less is a small project, twenty man  years or more is a large project.

Software project management should define a life cycle approach and documentation plan that reflects these factors.

Projects which use any commercial software must procure  software against stated requirements. Projects are not expected to reproduce design and implementation documentation about commercial software. The maintenance of such software is a responsibility of the  supplier.

The procedures for software production may be embedded in the infrastructure of the working environment; once these procedures have   been established, repetitive documentation of them is unnecessary.  Groups running many projects should ensure that their working  practices conform to the ESA Software Engineering Standards. Project           documentation should reference these practices.

Large, complex software projects may need to extend these  standards. Such projects may need to give more detailed consideration   to the procedural and life cycle aspects when there are changing  requirements or multiple contractors working in parallel.

### 4.2       Applying the Standards in a system development

Software developed for ESA is frequently part of a larger     system, satellite systems being an obvious example.  In this situation a number of activities will already have been performed at `system level' (as part of the system development life cycle) before the life cycle for any software part of the system can commence.

It is a `systems engineering' function to define the overall     requirements for the system to be built, often expressed in a System Requirement Document (often referred to as an SRD, but not to be  confused with a Software Requirements Document).  From this system  requirements document a decomposition into subsystems is often     performed with resulting subsystem specifications.  Trade-offs are done to partition the system/subsystems into hardware and software,  applying criteria specific to the system to be built (e.g. commonality, reliability, criticality etc).  Once the need for a  software item has been established, its life cycle, as defined in this standard, an begin.  Each of the software items identified in the system will have its individual life cycle.

Many of the user requirements may well exist in the system     documentation.  It is a false economy to assume that system     requirements are sufficient input to the development of a software  subsystem. To ensure some consistency in the input to a software     project, a User Requirements Document (URD) should always be produced.  The URD hould be traceable to the system and/or subsystem documentation.

The responsibilities for the production and change control of the URD should be agreed between `system' and `software' project     management, and recorded in the Software Project Management Plan.

### 4.3       Methods and tools

These standards do not make the use of any particular software ingineering method or tool mandatory.  The Standards describe the mandatory practices, recommended practices and guidelines for software ngineering projects, and allow each project to decide the best way of mplementing them.

References to methods and tools do appear, however, in these standards for two reasons.  Firstly, terminology from particular methods becomes, with time, part of computing vocabulary. Secondly, examples of possible ways of implementing the Standards are useful.

# P a r t  1   P r o d u c t   S t a n d a r d s

# CHAPTER 1: THE SOFTWARE LIFE CYCLE

## 1.1       INTRODUCTION

This chapter defines the overall software life cycle. The individual phases of the life cycle are described in more detail in  subsequent chapters.

In these Standards the term `software development project' is  often used. Clearly the development of software also involves computer hardware spects.  Trade-offs between hardware and software are part of designing a omputerised system, except when the hardware configuration is predefined, and constrains the software design.

## 1.2       PHASES, ACTIVITIES AND MILESTONES

The software life cycle starts when a software product is conceived and ends when it is no longer available for use, i.e. it     contains the whole of the development, operations and maintenance activities.

The products of a software development project shall be     delivered in a timely manner and be fit for their purpose. Software development activities shall be systematically planned and carried out. A `life cycle model' structures project activities into `phases'  and defines what activities occur in which phase. Figure 1.2 shows the life ycle model used in these Standards.

A `life cycle approach' is a combination of the basic phases of  the life cycle model. Section 1.3 describes three possible life cycle approaches which cover most of the needs of the Agency.

All software projects shall have a life cycle approach which  includes the basic phases shown in Figure 1.2:

UR phase    -     Definition of the user requirements

SR phase    -     Definition of the software requirements

AD phase    -     Definition of the architectural design

DD phase    -     Detailed design and production of the code

TR phase    -     Transfer of the software to operations

OM phase    -     Operations and maintenance

Figure 1.2: The Software Life Cycle Model

The first four phases end with a review, denoted by '/R' (e.g.  UR/R is the User Requirements Review).  These phases must occur  whatever the size, the application (e.g. scientific, administrative,   real time, batch), the hardware, the operating system or programming   language used, or whether the project is carried out by in-house staff or by ndustry. Each of these factors, however, influences the development approach, nd the style and content of the deliverable items.

In Figure 1.2 the heavy black line marks the boundary of the  software life cycle. This begins with the delivery of the User Requirements Document (URD) to the developer for review.  The UR/R is  the first activity of the software life cycle.  Following the approval of the URD, three `development' phases must take place  before the software is transferred to the users for operations. The deliverables of each phase must be reviewed and approved before proceeding to the next.  After a period of operations, the software is retired.  This event marks the end of the software life cycle.

There are six major milestones that mark progress in the  software life cycle.  These milestones, shown in Figure 1.2 as filled triangles, are the:

- approval of the User Requirements Document (URD);

- approval of the Software Requirements Document (SRD);

- approval of the Architectural Design Document (ADD);

- approval of the Detailed Design Document (DDD), the Software User Manual (SUM), the code, and the statement of readiness for  provisional acceptance testing;

- statement of provisional acceptance and the delivery of the  Software Transfer Document (STD);

- statement of final acceptance and the delivery of the Project   History Document (PHD).

The last milestone does not fall at the end of a phase, but at the end of the warranty period.

These milestones have been selected as the minimum necessary  for a workable contractual relationship.  They must be present in all projects. In long projects, additional milestones should be added to measure the progress of deliverables.

### 1.2.1     UR phase: user requirements definition

The UR phase is the `problem definition phase' of a software project. The scope of the system must be defined. The user  requirements must be captured.  This may be done by interview or  survey, or by building prototypes.  Specific user requirements must be identified and documented in the User Requirements Document (URD).

The involvement of the developers in this phase varies  according to the familiarity of the users with software. Some users  can produce a high quality URD, while others may need help from the   developers.

The URD must always be produced. The review of the URD is done    by the users, the software and hardware engineers and the managers  concerned. The approved URD is the input to the SR phase.

Before the completion of the User Requirements Review (UR/R), a  Software Project Management Plan outlining the whole project must be   produced by the developer.  This plan must contain a cost estimate for the project.  Detailed plans for the SR phase must also be produced.

### 1.2.2     SR phase: software requirements definition

The SR phase is the `analysis' phase of a software project.  A vital part of the analysis activity is the construction of a `model' describing `what' the software has to do, and not `how' to do it.   Building prototypes to clarify the software requirements may be necessary.

The principal deliverable of this phase is the Software Requirements Document (SRD). The SRD must always be produced for  every software project. Implementation terminology should be omitted from the SRD. The SRD must be reviewed formally by the users, by the computer hardware and software engineers, and by the managers concerned, during the Software Requirements Review (SR/R).

During the SR phase, the section of the Software Project Management Plan outlining the rest of the project must be updated.  The plan must contain an estimate of the total project cost, and best  efforts should be made to achieve an accuracy of at least 30%. Detailed plans for the AD phase must also be produced.

### 1.2.3     AD phase: architectural design

The purpose of the AD phase is to define the structure of the software. The model constructed in the SR phase is the starting point.

This model is transformed into the architectural design by allocating functions to software components and defining the control and data  flow between them.

This phase may involve several iterations of the design. Technically difficult or critical parts of the design have to be identified. Prototyping of these parts of the software may be necessary to confirm the basic design assumptions.  Alternative designs may be proposed, one of which must be selected.

The deliverable item which constitutes the formal output of  this phase is the Architectural Design Document (ADD). The ADD must always be produced for every software project. The ADD must be reviewed formally by the computer hardware and software engineers, by the users, and by the management concerned, during the Architectural          Design Review (AD/R).

During the AD phase, a Software Project Management Plan outlining the rest of the project must be produced.  This plan must contain an estimate of the project cost, and best efforts should be made to achieve an accuracy of at least 10%. Detailed plans for the DD phase must also be produced.

### 1.2.4     DD phase: detailed design and production

The purpose of the DD phase is to detail the design of  the  software, and to code, document and test it.

The Detailed Design Document (DDD) and the Software User Manual (SUM) are produced concurrently with coding and testing. Initially,   the DDD and SUM contain the sections corresponding to the top levels of the system. As the design progresses to lower levels, related  subsections are added. At the end of the phase, the documents are completed and, with the code, constitute the deliverable items of this phase.

During this phase, unit, integration and system testing activities are performed according to verification plans established in the SR and AD phases. As well as these tests, there have to be checks on the software quality.

The three deliverable items (Code, DDD, SUM), which have already been the subject of intermediate reviews during the DD phase,   must be formally reviewed by the software engineers and the management concerned, during the Detailed Design Review (DD/R). At the end of the review process, the software can be declared ready for provisional acceptance testing.

### 1.2.5     TR phase: transfer

The purpose of this phase is to establish that the software  fulfils the requirements laid down in the URD. This is done by installing the software and conducting acceptance tests.

When the software has been demonstrated to provide the required capabilities, the software can be provisionally accepted and operations started.

The Software Transfer Document (STD) must be produced during the TR phase to document the transfer of the software to the  operations team.

### 1.2.6     OM phase: operations and maintenance

Once the software has entered into operation, it should be carefully monitored to confirm that it meets all the requirements  defined in the URD. Some of the requirements, for example those for  availability, may take a period of time to validate. When the software has passed all the acceptance tests, it can be finally accepted.

The Project History Document (PHD) summarises the significant managerial information accumulated in the course of the project. This  document must be issued after final acceptance. It should be reissued  at the end of the life cycle, with information gathered in the OM    phase.

After final acceptance, the software may be modified to correct  errors undetected during earlier phases, or because new requirements arise. This is called `maintenance'.

For the whole period of operation, particular attention should be paid to keeping the documentation up-to-date. Information on faults and failures should be recorded to provide the raw data for the establishment of software quality metrics for subsequent projects.  Tools should be used to facilitate the collection and analysis of quality data.

## 1.3       LIFE CYCLE APPROACHES

The software life cycle model, shown in Figure 1.2, summarises  the phases and activities which must occur in any software project. A life cycle approach, based upon this model, should be defined, for each project, in the Software Project Management Plan.

This section defines three approaches which cover most of the needs of the Agency.  In the diagrams, the phases of Figure 1.2 have  been reduced to boxes. Arrows connecting the boxes represent permitted transitions.

### 1.3.1     The waterfall approach

Figure 1.3.1: The waterfall approach

The `waterfall' approach, shown in Figure 1.3.1, is the  simplest interpretation of the model shown in Figure 1.2.  The phases  are executed sequentially, as shown by the heavy arrows.  Each phase is executed once, although iteration of part of a phase is allowed for error correction, as shown by the dashed arrows.  Delivery of the complete system occurs at a single milestone at the end of the TR phase. The approach allows the contractual relationship to be simple.

### 1.3.2     The incremental delivery approach

Figure 1.3.2: The incremental delivery approach

The `incremental delivery' approach, shown in Figure 1.3.2, is characterised by splitting the DD, TR and OM phases into a number of more manageable units, once the complete architectural design has  been defined. The software is delivered in multiple releases, each   with increased functionality and capability. This approach is beneficial for large projects, where a single delivery would not be practical.  This may occur for a number of reasons such as:

- certain functions may need to be in place before others can be   effective;

- the size of the development team may necessitate subdivision of   the project into a number of deliveries;

- budgeting considerations may only allow partial funding over a  number of years.

In all cases, each deliverable should be usable, and provide a  subset of the required capabilities.

A disadvantage of the incremental delivery approach is that regression testing is required to confirm that existing capabilities   of the software are not impaired by any new release.   The increased  amount of testing required increases the cost of the software.

### 1.3.3     The evolutionary development approach

Figure 1.3.3: The evolutionary development approach

(Available only on hard copy)

The `evolutionary' approach, shown in Figure 1.3.3, is  characterised by the planned development of multiple releases.  All  phases of the life cycle are executed to produce a release. Each release incorporates the experience of earlier releases. The evolutionary approach may be used because, for example:

- some user experience is required to refine and complete the requirements (shown by the dashed line within the OM boxes);

- some parts of the implementation may depend on the availability  of future technology;

- some new user requirements are anticipated but not yet known;

- some requirements may be significantly more difficult to meet than others, and it is decided not to allow them to delay a  usable delivery.

The dashed extensions to the boxes in Figure 1.3.3 show that some overlap of OM phases will occur until each new delivery is finally accepted.

In an evolutionary development, the developer should recognise the user's priorities and produce the parts of the software that are both important to the user and, possible to develop with minimal  technical problems or delays.

The disadvantage of the evolutionary approach is that if the requirements are very incomplete to start with, the initial software structure may not bear the weight of later evolution. Expensive rewrites may be necessary.  Even worse, temporary solutions may become embedded in the system and distort its evolution. Further, users may become impatient with the teething troubles of each new release. In each development cycle, it is important to aim for a complete statement of requirements (to reduce risk) and an adaptable design (to ensure later modifiability).  In an evolutionary development, all requirements do not need to be fully implemented in each development cycle. However, the architectural design should take account of all known requirements.

## 1.4       PROTOTYPING

The use of prototypes to test customer reaction and design  ideas is common to many engineering disciplines. A software prototype  implements selected aspects of proposed software so that tests, the most direct kind of verification, can be carried out.

Prototyping is the process of building prototypes. Prototyping within a single phase is a useful means of reducing the risk in a project through practical experience. The output of a prototyping exercise is the knowledge that is gained from implementing or using  the prototype software.

The objective of the prototyping activity should be clearly stated before the process starts.  Prototyping to define requirements  is called `exploratory' prototyping, while that for investigating the feasibility of proposed solutions is called `experimental'  prototyping.

Prototypes usually implement high risk functional, performance  or user interface requirements and usually ignore quality,  reliability, maintainability and safety requirements. Prototype software is therefore `pre-operational' and should never be delivered as part of an operational system.

## 1.5       HANDLING REQUIREMENTS CHANGE

The URD and SRD must be `complete' documents. This means that all known requirements must be included when they are produced.

Nevertheless, it is possible that new requirements may arise after the URD and SRD have been approved.  Procedures for handling new requirements should be established at the beginning of the project.

Design integrity should not be compromised when new requirements are incorporated.  Such requirements, if accepted by  both user and developer, should be handled in the same way as the original requirements.  The procedure for handling a new user  requirement is therefore to:

- generate a new draft of the URD,

- convene a UR review and, if the change is accepted, then

- repeat the SR, AD and DD phases to incorporate the new requirement and its consequences.

A new software requirement is handled in a similar way.

An alternative method for handling new requirements is to  institute a Software Review Board after the UR/R instead of after the DD/R.  Another method is to use the evolutionary development life cycle approach.  However, this merely defers the handling of new requirements to the release following the one that is in preparation,  and this may not be sufficient.

The quality of the work done in the UR and SR phases can be   measured by the number of requirements that appear in later phases.

Especially important is the trend in the occurrence of new  requirements.  An upward trend is a sure sign that the software is  unlikely to be a success.

The availability of software engineering tools may be critical to the success of a project with frequently changing requirements.

In projects where requirements are agreed and frozen at the end of  the SR phase, the use of paper-based methods for requirements analysis and design specification may be sufficient.  In projects  where the freezing of requirements is not possible, software engineering tools that allow new requirements and design changes to be assimilated quickly may be essential to avoid serious delays.

# CHAPTER 2: THE USER REQUIREMENTS DEFINITION PHASE

## 2.1       INTRODUCTION

The UR phase can be called the `problem definition phase' of   the life cycle. The purpose of this phase is to refine an idea about a task to be performed, using computing equipment, into a definition of what is expected from the computer system.

The definition of the user requirements shall be the responsibility of the user. The expertise of software engineers, hardware engineers and operations personnel should be used to help  define and review the user requirements.

An output of the UR phase is the User Requirements Document  (URD). This is a critical document for the whole software project   because it defines the basis upon which the software is accepted.

The UR phase terminates with formal approval of the URD by the User Requirements Review (UR/R).

## 2.2       INPUTS TO THE PHASE

No formal inputs are required, although the results of  interviews, surveys, studies and prototyping exercises are often  helpful in formulating the user requirements.

## 2.3       ACTIVITIES

The main activity of the UR phase is to capture the user   requirements and document them in the URD.  The scope of the software  has to be established and the interfaces with external systems  identified.

Plans of SR phase activities must be drawn up in the UR phase.  These plans should cover project management, configuration  management, verification, validation and quality assurance.  These  activities are described in more detail in Part 2.

### 2.3.1     Capture of user requirements

While user requirements originate in the spontaneous perception of needs, user requirements should be clarified through the criticism and experience of existing software and prototypes. The widest  possible agreement about the user requirements should be established    through interviews and surveys.  The knowledge and experience of the  potential development organisations should be used to advise on  implementation feasibility, and, perhaps, to build prototypes. User  requirements definition is an iterative process, and requirements  capture activities may have to be repeated a number of times before the URD is ready for review.

### 2.3.2     Determination of operational environment

Determining the operational environment should be the first step in defining the user requirements.  A clear account should be  developed of the real world in which the software is to operate. This narrative description may be supported by context diagrams, to  summarise the interfaces with external systems (often called  `external interfaces'), and system block diagrams, to show the role  of the software in a larger system.

The nature of exchanges with external systems should be specified and controlled from the start of the project.  The  information may reside in an Interface Control Document (ICD), or in the design documentation of the external system.  If the external  system already exists, then the exchanges may already be defined in some detail, and constrain the design. Alternatively, the definition of the external interfaces may develop throughout the UR, SR and AD  phases.

### 2.3.3     Specification of user requirements

When the operational environment has been established, specific user requirements are extracted and organised. Implementation  considerations are omitted, unless they are the essence of the  requirement.

2.3.3.1   Classification of user requirements

User requirements fall into two categories:

- capabilities needed by users to solve a problem or achieve an objective;

- constraints placed by users on how the problem is to be solved or the objective achieved.

Capability requirements describe functions and operations needed by users. Quantitative statements that specify performance and  accuracy attributes should form part of the specification of a capability.

Space and time dimensions can be useful for organising capability requirements. It is often convenient to describe  capability requirements in terms of a sequence of operations.

Constraint requirements place restrictions on how software can be built and operated. For example, definitions of external  communications, hardware and software interfaces may already exist, either because the software is a part of a larger system, or because  the user requires that certain protocols, standards, computers,           operating systems, library or kernel software be used.

The Human-Computer Interaction (HCI) requirements will vary according to the type of software under consideration.  For  interactive systems, the users may wish to provide examples of the dialogue that is required, including the hardware to be used (e.g.  keyboard, mouse, colour display etc), and assistance provided by the           software (e.g. online help).  For batch systems, it may be sufficient to indicate the parameters that need to be varied and the output   medium and format required.

Constraints that users may wish to place on the software include the quality attributes of adaptability, availability,   portability and security. The user shall describe the consequences of  losses of availability, or breaches of security, so that developers  can fully appreciate the criticality of each function.

The user may choose to make additional standards applicable; such requirements are additional constraints on the development.

2.3.3.2   Attributes of user requirements

Each user requirement must include the attributes listed below.

(a)   Identifier - each user requirement shall include an identifier, to facilitate tracing through subsequent phases.

(b)   Need - essential user requirements shall be marked as such. Essential user requirements are non-negotiable; others may be  less vitally important and subject to negotiation.

(c)   Priority - for incremental delivery, each user requirement  shall include a measure of priority so that the developer can   decide the production schedule.

(d)   Stability - some user requirements may be known to be stable  over the expected life of the software; others may be more  dependent on feedback from the SR, AD and DD phases, or may be subject to change during the software life cycle. Such unstable  requirements should be flagged.

(e)   Source - the source of each user requirement shall be stated. This may be a reference to an external document (e.g. system   requirement document) or the name of the user, or user group, that provided the user requirement.

(f)   Clarity - a user requirement is clear if it has one, and only one, interpretation. Clarity implies lack of ambiguity.  If a  term used in a particular context has multiple meanings, the  term should be qualified or replaced with a more specific term.

(g)   Verifiability - each user requirement shall be verifiable. This  means that it must be possible to:

check that the requirement has been incorporated in the design;

prove that the software will implement the requirement;

test that the software does implement the requirement.

### 2.3.4     Reviews

The outputs of the UR phase shall be formally reviewed during  the User Requirements Review (UR/R). This should be a technical  review (see Part 2, Chapter 4). Participants should include the   users, operators, developers (hardware and software engineers) and  the managers concerned.

User requirements which are rejected in the review process do not have to be removed from the URD, especially if it is anticipated   that resources may be available at some later date to implement them.

Non-applicable user requirements shall be clearly flagged in the URD.

## 2.4       OUTPUTS FROM THE PHASE

The main outputs of the phase are the URD and the plans for the      SR phase.

### 2.4.1     User Requirements Document

An output of the UR phase shall be the User Requirements   Document (URD).  The URD shall always be produced before a software   project is started. The recommended table of contents for the URD is provided in Appendix C.

The URD shall provide a general description of what the user xpects the software to do. All known user requirements shall be  included in the URD. The URD should state the specific user requirements as clearly and consistently as possible.

The URD shall describe the operations the user wants to perform  with the software system. The URD shall define all the constraints    that the user wishes to impose upon any solution. The URD shall   describe the external interfaces to the software system, or reference    them in ICDs that exist or are to be written.

Change control of the URD should be the responsibility of the   user. If a user requirement changes after the URD has been approved,    then the user should ensure that the URD is changed and resubmitted  to the UR/R board for approval.

### 2.4.2     Acceptance test plans

Acceptance test plans must be defined in the acceptance test section of the Software Verification and Validation Plan    (SVVP/AT/Plans, see Part 2, Chapter 4).  These plans outline the   approach to demonstrating that the software will meet the user   requirements.

### 2.4.3     Project management plan for the SR phase

The outline project plan, the estimate of the total project  cost, and the management plan for the SR phase, must be documented in    the SR phase section of the Software Project Management Plan

(SPMP/SR, see Part 2, Chapter 2).

### 2.4.4     Configuration management plan for the SR phase

The configuration management procedures for the documents, CASE  tool products and prototype software, to be produced in the SR phase,     must be documented in the Software Configuration Plan (SCMP/SR, see Part 2, Chapter 3).

### 2.4.5     Verification and validation plan for the SR phase

The SR phase review and traceability procedures must be  documented in the Software Verification and Validation Plan (SVVP/SR,   see Part 2, Chapter 4).

### 2.4.6     Quality assurance plan for the SR phase

The SR phase quality monitoring procedures must be defined in the Software Quality Assurance Plan (SQAP/SR, see Part 2, Chapter 5).

# CHAPTER 3:    THE SOFTWARE REQUIREMENTS DEFINITION PHASE

## 3.1       INTRODUCTION

The SR phase can be called the `problem analysis phase' of the life cycle. The purpose of this phase is to analyse the statement of  user requirements in the URD and produce a set of software requirements as complete, consistent and correct as possible.

The definition of the software requirements is the  responsibility of the developer.  Participants in this phase should  include users, software engineers, hardware engineers and operations personnel.  They all have a different concept of the end product, and  these concepts must be analysed, and then synthesised, into a complete and consistent statement of requirements about which  everyone can agree. Project management should ensure that all parties           are consulted, so that the risk of incompleteness and error is minimised.

An output of this phase is the Software Requirements Document (SRD). As well as defining `what' the product must do, it is also the  reference against which both the design and the product will be verified.  Although `how' aspects may have to be addressed, they  should be eliminated from the SRD, except those that constrain the          software.

The software requirements definition phase terminates with  formal approval of the SR phase outputs by the Software Requirements  Review (SR/R).

## 3.2       INPUTS TO THE PHASE

The inputs to the SR phase are the:

- User Requirements Document (URD);

- Software Project Management Plan for the SR phase (SPMP/SR);

- Software Configuration Management Plan for the SR phase   (SCMP/SR);

- Software Verification and Validation Plan for the SR phase   (SVVP/SR);

- Software Quality Assurance Plan for the SR phase (SQAP/SR).

## 3.3       ACTIVITIES

SR phase activities shall be carried out according to the plans defined in the UR phase.  Progress against plans should be  continuously monitored by project management and documented at regular intervals in progress reports.

The main SR phase activity is to transform the user requirements stated in the URD into the software requirements stated in the SRD.   This is achieved by analysing the problem, as stated in the URD, and building a coherent, comprehensive description of what the software is to do.  The SRD contains a developer's view of the         problem, rather than the user's.  This view should be based upon a model of the system, built according to a recognised, documented method.

Software requirements may require the construction of prototypes to clarify or verify them.  Requirements which cannot be justified by modelling, or whose correctness cannot be demonstrated in a formal way, may need to be prototyped. User interface requirements often need this kind of `exploratory prototyping'.

Plans of AD phase activities must be drawn up in the SR phase. These plans must cover project management, configuration management, verification, validation and quality assurance.  These activities are described in more detail in Part 2.

### 3.3.1     Construction of the logical model

The developer shall construct an implementation-independent model of what is needed by the user. This is called a `logical model', and it is used to produce the software requirements.

The logical model may be constructed by top-down decomposition of the main function, as inferred from  the URD, into a hierarchy of functions. Modelling is an iterative process. Parts of the model may need to be respecified many times before a complete, coherent and consistent description is achieved.

Walkthroughs, reviews and inspections should be used to ensure that the specification of each level has been agreed before proceeding to the next level of detail. A good quality logical model should satisfy the rules listed below.

(1)   Functions should have a single definite purpose.  Function   names should have a declarative structure (e.g. `Validate Telecommands'), and say `what' is to be done rather than `how'.  Good naming allows design components with strong  cohesion to be easily derived (see Part 1, Section 4.3.1.3).

(2)   Functions should be appropriate to the level at which they  appear (e.g. `Calculate Checksum' should not appear at the same level as `Verify Telecommands').

(3)   Interfaces should be minimised. This allows design components with weak coupling to be easily derived (see Part 1, Section  4.3.1.3).

(4)   Each function should be decomposed into no more than seven sub-functions.

(5)   The model should omit implementation information (e.g. file,  record, task, module);

(6)   The performance attributes of each function (capacity, speed, etc) should be stated;

(7)   Critical functions should be identified.  In all but the smallest projects, CASE tools should be used for

building a logical model. They make consistent models easier to  construct and modify.

### 3.3.2     Specification of software requirements

The software requirements are obtained by examining the model and classifying them in terms of:

(a)   Functional requirements

(b)   Performance requirements

(c)   Interface requirements

(d)   Operational requirements

(e)   Resource requirements

(f)   Verification requirements

(g)   Acceptance testing requirements

(h)   Documentation requirements

(i)   Security requirements

(j)   Portability requirements

(k)   Quality requirements

(l)   Reliability requirements

(m)   Maintainability requirements

(n)   Safety requirements

While other classifications of requirements can be conceived, developers should use this classification, with the definitions   described in Section 3.3.2.1.

Software requirements should be rigorously described. Various alternatives to natural language are available and their use is encouraged. Wherever possible, software requirements should be stated in quantitative terms to increase their verifiability.

As the requirements are compiled, they must include identifiers, references and measures of need, priority and stability. The requirements must be complete and consistent. Duplication is to   be avoided.

3.3.2.1   Classification of software requirements

(a)   Functional requirements. These specify `what' the software has to do. They define the purpose of the software.  The functional  requirements are derived from the logical model, which is in turn derived from the user's capability requirements. In order  that they may be stated quantitatively, the functional requirements may include performance attributes.

(b)   Performance requirements. These specify numerical values for  measurable variables (e.g. rate, frequency, capacity, and  speed). Performance requirements may be incorporated in the quantitative specification of each function, or stated as  separate requirements. Qualitative statements are unacceptable (e.g. replace `quick response' with `response time must be less  than x seconds for y% of the cases with an average response time of less than z seconds'). The performance attributes may  be presented as a range of values, for example the:

worst case that is acceptable;

nominal value, to be used for planning;

best case value, to indicate where growth potential is needed.

(c)   Interface requirements. These specify hardware, software or database elements with which the system, or system component,  must interact or communicate. Interface requirements should be classified into software, hardware and communications  interfaces. Software interfaces  could include operating systems, software environments, file formats,  database management systems and other software applications. Hardware interface requirements may specify the hardware  configuration. Communications interface requirements constrain the nature of the interface to other hardware and software. They may demand the use of a particular network protocol, for example. External interface requirements should be described,  or referenced in ICDs. User interface requirements should be specified under `Operational Requirements' (see below).

Interface requirements can be illustrated with system block diagrams (e.g. to show the hardware configuration).

(d)   Operational requirements. These specify how the system will run and how it will communicate with the human operators.  Operational requirements include all user interface, man-machine or human-computer interaction requirements as well  as the logistical and organisational requirements. Examples  are: the screen layout, the content of error messages, help systems etc. It is often useful to define the semantics and syntax of commands.

(e)   Resource requirements. These specify upper limits on physical resources such as processing power, main memory, disc space etc. These are especially needed when extension of processing hardware late in the life cycle becomes too expensive, as in many embedded systems.

(f)   Verification requirements. These specify the constraints on how the software is to be verified. The verification requirements constrain the SVVP. They might include requirements for simulation, emulation, live tests with simulated inputs, live tests with real inputs, and interfacing with the testing environment.

(g)   Acceptance testing requirements. These specify the constraints on how the software is to be validated. The acceptance testing requirements constrain the SVVP.

(h)   Documentation requirements. These specify project-specific requirements for documentation in addition to those contained in these standards (e.g. the detailed format of the Software User Manual).

(i)   Security requirements. These specify the requirements for securing the system against threats to confidentiality, integrity and availability. Examples of security requirements are interlocking operator commands, inhibiting of commands, read-only access, password system and computer virus protection.  The level of physical protection needed of the computer facilities may also be stated (e.g. backups are to be kept in a fire-proof safe off-site).

(j)   Portability requirements. These specify the ease of modifying the software to execute on other computers and operating systems. Possible computers and operating systems, other than those of the target system, should be stated.

(k)   Quality requirements. These specify attributes of the software that ensure that it will be fit for its purpose (other than the major quality attributes of reliability, maintainability and safety, which should always be specified).  Where appropriate, software quality attributes should be specified in measurable terms (i.e. with the use of metrics).

(l)   Reliability requirements. These specify the acceptable mean time interval between failures of the software, averaged over a significant period (MTTF).  They may also specify the minimum time between failures that is ever acceptable. Reliability requirements may have to be derived from the user's availability requirements.

(m)   Maintainability requirements. These specify how easy it is to repair faults and adapt the software to new requirements.  The ease of performing these tasks should be stated in quantitative terms, such as mean time to repair a fault (MTTR). They may include constraints imposed by the potential maintenance organisation. Maintainability requirements may be derived from the user's availability and adaptability requirements.

(n)   Safety requirements. These specify any requirements to reduce the possibility of damage that can follow from software failure. Safety requirements may identify critical functions whose failure may be hazardous to people or property.

3.3.2.2   Attributes of software requirements

Each software requirement must include the attributes listed

below.

(a)   Identifier - each software requirement shall include an identifier, to facilitate tracing through subsequent phases.

(b)   Need - essential software requirements shall be marked as such. Essential software requirements are non-negotiable; others may be less vitally important and subject to negotiation.

(c)   Priority - for incremental delivery, each software requirement shall include a measure of priority so that the developer can decide the production schedule.

(d)   Stability - some requirements may be known to be stable over the expected life of the software; others may be more dependent on feedback from the design phase, or may be subject to change during the software life cycle. Such unstable requirements should be flagged.

(e)   Source - references that trace software requirements back to the URD shall accompany each software requirement.

(f)   Clarity - a requirement is clear if it has one, and only one, interpretation. Clarity implies lack of ambiguity.  If a term used in a particular context has multiple meanings, the term should be qualified or replaced with a more specific term.

(g)   Verifiability - each software requirement shall be verifiable.

This means that it must be possible to:

- check that the requirement has been incorporated in the  design;

- prove that the software will implement the requirement;

- test that the software does implement the requirement.

3.3.2.3   Completeness of software requirements

Completeness has two aspects:

- no user requirement has been overlooked;

- an activity has been specified for every possible set of inputs.

For the SRD to be complete, each requirement in the URD must be accounted for.  A traceability matrix must be inserted in the SRD to prove completeness.

The phrase `To Be Defined' (TBD) indicates incompleteness. There must be no TBDs in the SRD.

3.3.2.4   Consistency of software requirements

A set of requirements is consistent if, and only if, no set of individual requirements conflict. There are a number of types of inconsistency, for example:

- different terms used for the same thing;

- the same term used for different things;

- incompatible activities happening at the same time;

- activities happening in the wrong order.

The achievement of consistency is made easier by using methods and tools.

3.3.2.5   Duplication of software requirements

Duplication of requirements should be avoided, although some duplication may be necessary if the SRD is to be understandable.

There is always a danger that a requirement that overlaps or duplicates another will be overlooked when the SRD is updated. This leads to inconsistencies.  Where duplication occurs, cross-references should be inserted to enhance modifiability.

### 3.3.3     Reviews

The outputs of the SR phase shall be formally reviewed during the Software Requirements Review (SR/R). This should be a technical review (see Part 2, Chapter 4). Participants should include the users, the operations personnel, the developers and the managers concerned.

## 3.4       OUTPUTS FROM THE PHASE

The main outputs of the phase are the SRD and the plans for the AD phase.

Progress reports, configuration status accounts, and audit reports are also outputs of the phase.  These should always be archived by the project.

### 3.4.1     Software Requirements Document

An output of the SR phase shall be the Software Requirements Document (SRD).

The SRD shall be complete. The SRD shall cover all the requirements stated in the URD.  A table showing how user requirements correspond to software requirements shall be placed in the SRD.  This demonstrates forwards traceability and can be used to prove completeness.

The SRD shall be consistent.  Software engineering methods and tools can help achieve consistency.

The functional requirements should be structured top-down in the SRD. Non-functional requirements should be attached to functional requirements and therefore can appear at all levels of the hierarchy, and apply to all functional requirements below them (inheritance of family attributes).

The SRD shall not include implementation details or terminology, unless it has to be present as a constraint.

Descriptions of functions, therefore, shall say what the software is to do, and must avoid saying how it is to be done. The SRD shall avoid specifying the hardware, unless it is a constraint placed by the user.

The outputs of the analysis method, for example `data flow diagrams' in the case of Structured Analysis, should be included, so as to provide the overview needed to permit an understanding of the specific requirements.

Each software requirement must have an identifier, and include measures of need and priority.  Software requirements must reference the URD to facilitate backwards traceability.

The SRD may be written in a natural language. This has the important advantage that it presents no additional barriers between the people of different disciplines who are involved during this phase. On the other hand, natural languages have many properties that are undesirable in specifications (ambiguity, imprecision and inconsistency). Using requirements specification languages can eliminate many of these problems, and these range in rigor from Structured English to  Formal Methods such as Z or VDM. Formal methods should be considered for the specification of safety-critical systems. If a requirements specification language is used, explanatory text, written in natural language, should be included in the SRD to enable it to be reviewed by those not familiar with the specification language.

The SRD shall be compiled according to the table of contents provided in Appendix C, which is derived from ANSI/IEEE Std 830-1984, Software Requirements Specifications.

### 3.4.2     System test plans

System test plans must be defined in the system test section of the Software Verification and Validation Plan (SVVP/ST/Plans, see Part 2, Chapter 4).  These plans outline the approach to demonstrating that the software will meet the software requirements.

### 3.4.3     Project management plan for the AD phase

The outline project plan, the cost estimate for the complete project (accurate to 30%), and the management plan for the AD phase, must be documented in the AD phase section of the Software Project Management Plan (SPMP/AD, see Part 2, Chapter 2).

### 3.4.4     Configuration management plan for the AD phase

The configuration management procedures for the documents, CASE tool products and prototype software, to be produced in the AD phase, must be documented in the Software Configuration Management Plan (SCMP/AD, see Part 2, Chapter 3).

### 3.4.5     Verification and validation plan for the AD phase

The AD phase review and traceability procedures must be documented in the Software Verification and Validation Plan (SVVP/AD, see Part 2, Chapter 4).

### 3.4.6     Quality assurance plan for the AD phase

The AD phase quality monitoring procedures must be defined in the Software Quality Assurance Plan (SQAP/AD, see Part 2, Chapter 5).

# CHAPTER 4:  THE ARCHITECTURAL DESIGN PHASE

## 4.1       INTRODUCTION

The AD phase can be called the `solution phase' of the life cycle. The purpose of this phase is to define a collection of software components and their interfaces to establish a framework for developing the software.  This is the `Architectural Design', and it must cover all the requirements in the SRD.

The architectural design definition is the responsibility of the software engineers.  Other kinds of engineers may be consulted during this phase, and representatives of users and operations personnel should review the architectural design.

An output of this phase is the Architectural Design Document (ADD). This should document each component, and its relationship with other components.  The ADD is complete when the level of definition of components and interfaces is sufficient to enable individuals or small groups to work independently in the DD phase.

The architectural design phase terminates with formal approval of the AD phase outputs by the Architectural Design Review (AD/R).

## 4.2       INPUTS TO THE PHASE

The inputs to the AD phase are the:

- Software Requirements Document (SRD);

- Software Project Management Plan for the AD phase (SPMP/AD);

- Software Configuration Management Plan for the AD phase  (SCMP/AD);

- Software Verification and Validation Plan for the AD phase (SVVP/AD);

- Software Quality Assurance Plan for the AD phase (SQAP/AD).

## 4.3       ACTIVITIES

AD phase activities shall be carried out according to the plans defined in the SR phase.  Progress against plans should be continuously monitored by project management and documented at regular intervals in progress reports.

The principal activity of the AD phase is to develop the architectural design of the software and document it in the ADD.

This involves:

- constructing the physical model;

- specifying the architectural design;

- selecting a programming language;

- reviewing the design.

A recognised method for software design shall be adopted and applied consistently in the AD phase.  Where no single method provides all the capabilities required, a project-specific method may be adopted, which should be a combination of recognised methods.

Plans for the rest of the development must be drawn up in the AD phase. These plans cover project management, configuration management, verification, validation and quality assurance.  These activities are described in more detail in Part 2.

### 4.3.1     Construction of the physical model

The developer shall construct a `physical model' which describes the design of the software, using implementation terminology.  The physical model should be derived from the logical model, described in the SRD. In transforming a logical model to a physical model, `design decisions' are made in which functions are allocated to components and their inputs and outputs defined. Design decisions should also satisfy non-functional requirements, design quality criteria and implementation technology considerations. Design decisions should be recorded.

Modelling is an iterative process. Each part of the model needs to be specified and respecified until a coherent description of each component is achieved.

In all but the smallest projects, CASE tools should be used for building the physical model. They make consistent models easier to construct and modify.

4.3.1.1   Decomposition of the software into components

The software should be decomposed into a hierarchy of components according to a partitioning method.  Examples of partitioning methods are `functional decomposition' and `correspondence with real world objects'. There should be distinct levels within the hierarchy, with each component occupying a well-defined place.

The method used to decompose the software into its component parts shall permit a top-down approach.  Starting from the top-level component, the software is decomposed into a hierarchy of components.tectural design should specify the upper levels of the hierarchy, typically the top three or four.

Top-down decomposition is vital for controlling complexity because it enforces `information hiding' by demanding that lower-level components behave as `black boxes'.  Only the function and interfaces of a lower-level component are required for the higher-level design. The information necessary to the internal workings of a lower-level component can remain hidden.

Top-down decomposition also demands that each level of the design be described using terms that have an appropriate degree of `abstraction' (e.g. the terms `file', `record', and `byte' ought to occur at different levels in the design of a file-handling system).f the right degree of abstraction at each level assists information hiding.

The bottom-level components in the ADD should be sufficiently independent to allow their detailed design and coding to proceed in parallel to that of other components, with a minimum of interaction between programmers. In multi-tasking systems, the lowest level of the Architectural Design should be the task level. At the task level,g relationships (i.e. before, after or concurrent) between functions are used to allocate them to tasks.

4.3.1.2   Implementation of non-functional requirements

The SRD contains a number of requirements in the non-functional category.  These are:

- Performance requirements

- Interface requirements

- Operational requirements

- Resource requirements

- Verification requirements

- Acceptance testing requirements

- Documentation requirements

- Security requirements

- Portability requirements

- Quality requirements

- Reliability requirements

- Maintainability requirements

- Safety requirements

The design of each component should be reviewed against each of these requirements.  While some non-functional requirements may apply to all components in the system, other non-functional requirements may affect the design of only a few components.

4.3.1.3   Design quality criteria

Designs should be adaptable, efficient and understandable. Adaptable designs are easy to modify and maintain. Efficient designs make minimal use of available resources. Designs must be understandable if they are to be built, operated and maintained effectively.

Attainment of these goals is assisted by aiming for simplicity in form and function in every part of the design. There are a number of metrics that can be used for measuring complexity, (e.g. number of interfaces per component), and their use should be considered.

Simplicity of function is achieved by maximising the `cohesion' of individual components (i.e. the degree to which the activities internal to the component are related to one another).

Simplicity of form is achieved by:

- minimising the `coupling' between components (i.e. the number of distinct items that are passed between components);

- ensuring that the function a component performs is appropriate to its level in the hierarchy;

- matching the software and data structures;

- maximising the number of components that use a given component;

- restricting the number of child components to 7 or less;

- removing duplication between components by making new components.

Designs should be  `modular', with minimal coupling between components and maximum cohesion within each component.  There is minimal duplication between components in a modular design. Components of a modular design are often described as `black boxes' because they hide  internal information from other components.  It is

not necessary to know how a black box component works to know what to do with it.

Understandable designs employ terminology in a consistent way and always use the same solution to the same problem.  Where teams of designers collaborate to produce a design, understandability can be considerably impaired by permitting unnecessary variety. CASE tools,tandards and design reviews all help to enforce consistency and uniformity.

4.3.1.4   Trade-off between alternative designs

There is no unique design for any software system. Studies of the different options may be necessary. A number of criteria will be needed to choose the best option. The criteria depend on the type of system. For example, in a real-time situation, performance and response time could be important, whereas in an administrative system stability of the data base might be more important.

Prototyping may be performed to verify assumptions in the design or to evaluate alternative design approaches. This is called `experimental prototyping'. For example, if a program requires fast access to data stored on disc, then various methods of file access could be coded and measured. Different access methods could alter the design approach quite significantly, and prototyping the access method would become an essential part of the design process.

Only the selected design approach shall be reflected in the ADD (and DDD). However, the need for the prototyping, listing of code, criteria, and reasons for the chosen solution, should be documented in the Project History Document.

### 4.3.2     Specification of the architectural design

The architectural design is the fully documented physical model.  This should contain diagrams showing, at each level of the architectural design, the data flow and control flow between the components.  Block diagrams, showing entities such as tasks and files, may also be used to describe the design.  The diagramming techniques used should be documented or referenced.

4.3.2.1   Functional definition of the components

The process of architectural design results in a set of components having defined functions and interfaces. The functions of each component will be derived from the SRD. The level of detail in the ADD will show which functional requirements are to be met by each component, but not necessarily how to meet them: this will only be known when the detailed design is complete. Similarly, the interfaces between components will be restricted to a definition of the information to exchange, and not how to exchange it (unless this contributes to the success or failure of the chosen design).

For each component the following information shall be defined in the ADD:

- data input;

- functions to be performed;

- data output.

Data inputs and outputs should be defined as data structures   (see next section).

4.3.2.2   Definition of the data structures

Data structures that interface components shall be defined in the ADD. External interfaces may be separately documented in an ICD.

Data structure definitions shall include the:

- description of each element (e.g. name, type, dimension);

- relationships between the elements (i.e. the structure);

- range of possible values of each element;

- initial values of each element.

4.3.2.3   Definition of the control flow

The definition of the control flow between components is essential for the understanding of the software's operation.  The control flow between the components shall be defined in the ADD.

Control flow definitions may describe:

- sequential and parallel operations;

- synchronous and asynchronous behaviour.

4.3.2.4   Definition of the computer resource utilisation

The computer resources (e.g. CPU speed, memory, storage, system software)  needed in the development environment and the operational environment shall be estimated in the AD phase and defined in the ADD.  For many software projects, development environment and operational environment will be the same.  Any resource requirements

in the SRD will constrain the design.

### 4.3.3     Selection of programming languages

Programming languages should be selected that support top-down decomposition, structured programming and concurrent production and documentation.  The programming language and the AD method should be compatible.

Non-functional requirements may influence the choice of programming language. For example, portability and maintenance considerations suggest that assembler should be selected only for very specific and justifiable reasons. The availability of reliable compilers and effective debuggers constrains the selection of a programming language.

### 4.3.4     Reviews

The architectural design should be reviewed and agreed layer by layer as it is developed during the AD phase.  The design of any level invariably affects upper layers: a number of review cycles may be necessary before the design of a level can be finalised. Walkthroughs should be used to ensure that the architectural design is understood by all those concerned. Inspections of the design, by qualified software engineers, may be used to eliminate design defects.

The outputs of the AD phase shall be formally reviewed during the Architectural Design Review (AD/R).  This should be a technical review (see Part 2, Chapter 4). Participants should include the users, the operations personnel, the hardware engineers, software engineers, and the managers concerned.

After the start of the DD phase, modifications to the architectural design can increase costs substantially.  The DD phase should not be started if there are still doubts, major open points, or uncertainties in the architectural design.

## 4.4       OUTPUTS FROM THE PHASE

The main outputs of the phase are the ADD and the plans for the DD phase.

Progress reports, configuration status accounts, software verification reports and audit reports are also outputs of the phase. These should always be archived by the project.

### 4.4.1     Architectural Design Document

The Architectural Design Document (ADD) is the key document that summarises the solution.  It is the kernel from which the detailed design grows. The ADD shall define the major components of the software and the interfaces between them. The ADD shall define or reference all external interfaces. The ADD shall be an output from the AD phase.

The ADD shall be complete, covering all the software requirements described in the SRD.  To demonstrate this, a table cross-referencing software requirements to parts of the architectural design shall be placed in the ADD.

The ADD shall be consistent.  Software engineering methods and tools can help achieve consistency, and their output may be included in the ADD.

The ADD shall be sufficiently detailed to allow the project leader to draw up a detailed implementation plan and to control the overall project during the remaining development phases. The ADD should be detailed enough to enable the cost of the remaining development to be estimated to within 10%.

The ADD shall be compiled according to the table of contents provided in Appendix C, which is derived from ANSI/IEEE Std 1016-1987, Software Design Descriptions. This table of contents implements the approach described in Section 4.3.2.

### 4.4.2     Integration test plans

Integration test plans must be defined in the integration test section of the Software Verification and Validation Plan (SVVP/IT/Plans, see Part 2, Chapter 4).  These plans outline the approach to demonstrating that the software subsystems conform to the ADD.

### 4.4.3     Project management plan for the DD phase

The estimate of the total project cost (accurate to 10%), and the management plan for the DD phase, must be documented in the DD phase section of the Software Project Management Plan (SPMP/DD, see Part 2, Chapter 2). An outline plan for the TR and OM phases must also be included.

### 4.4.4     Configuration management plan for the DD phase

The configuration management procedures for the documents, deliverable code, CASE tool products and prototype software, to be produced in the DD phase, must be documented in the Software Configuration Management Plan (SCMP/DD, see Part 2, Chapter 3).

### 4.4.5     Verification and validation plan for the DD phase

The DD phase review and traceability procedures must be documented in the Software Verification and Validation Plan (SVVP/DD, see Part 2, Chapter 4).

### 4.4.6     Quality assurance plan for the DD phase

The DD phase quality monitoring procedures must be defined in the Software Quality Assurance Plan (SQAP/DD, see Part 2, Chapter 5).

This page is intentionally left blank

# CHAPTER 5:  THE DETAILED DESIGN AND PRODUCTION PHASE

## 5.1       INTRODUCTION

The DD phase can be called the `implementation phase' of the life cycle. The purpose of the DD phase is to detail the design outlined in the ADD, and to code, document and test it.

The detailed design and production is the responsibility of the software engineers.  Other kinds of engineers may be consulted during this phase, and representatives of users and operations personnel may observe system tests.

Important considerations before starting code production are the adequacy and availability of computer resources for software development. There is no point in starting coding and testing if the computer, operating system and system software are not available or sufficiently reliable and stable. Productivity can drop dramatically if these resources are not adequate. Failure to invest in software tools and development hardware often leads to bigger development costs.

The principal output of this phase are the code, the Detailed Design Document (DDD) and Software User Manual (SUM).

The DD phase terminates with formal approval of the code, DDD and SUM by the Detailed Design Review (DD/R).

## 5.2       INPUTS TO THE PHASE

The inputs to the DD phase are the:

- Architectural Design Document (ADD);

- Integration test plans (SVVP/IT/Plans);

- System test plans (SVVP/ST/Plans);

- Software Project Management Plan for the DD phase (SPMP/DD);

- Software Configuration Management Plan for the DD phase  (SCMP/DD);

- Software Verification and Validation Plan for the DD phase  (SVVP/DD);

- Software Quality Assurance Plan for the DD phase (SQAP/DD).

## 5.3       ACTIVITIES

DD phase activities shall be carried out according to the plans defined in the AD phase.  Progress against plans should be continuously monitored by project management and documented at regular intervals in progress reports.

The detailed design and production of software shall be based on the following three principles:

- top-down decomposition;

- structured programming;

- concurrent production and documentation.

These principles are reflected in both the software design and the organisation of the work. They help ensure that the software is delivered on time and within budget, because emphasis is placed on `getting it right first time'. They also have a positive effect on the quality of the software, its reliability, maintainability and safety.

Top-down decomposition is vital for controlling complexity because it enforces `information hiding' by demanding that lower-level components behave as `black boxes'.  Only the function and interfaces of a lower-level component are required for the higher-level design. The information necessary to the internal workings of a lower-level component can remain hidden.

Structured programming aims to avoid making errors when a module is designed and when code is written.  Stepwise refinement of a design into code, composed of the basic sequence, selection and iteration constructs is the main feature of the technique.  By reducing the number of coding errors, structured programming dramatically reduces time spent in testing and correcting software.d programming also makes code more understandable, reducing time spent in inspection and in maintenance.

Concurrent production and documentation of code is a side effect of stepwise refinement. Design information should be retained as commentary in the source code.

### 5.3.1     Detailed design

In detailed design, lower-level components of the architectural design are decomposed until they can be expressed as modules in the selected programming language.  A module is a program unit that is discrete and identifiable with respect to compiling, combining with other units, and loading.

Starting from the bottom-level components in the ADD, the design proceeds to lower levels via stepwise refinement of each module specification.

The guidelines for stepwise refinement are:

- start from functional and interface specifications;

- concentrate on the control flow;

- defer data declarations until the coding phase;

- keep steps of refinement small so that verification is easier;

- review each step as it is made.

The review of each module may be by walkthrough or inspection. The review of a module is complete when it is approved for coding.

The methods and CASE tools used for architectural design should be used in the DD phase for the detailed design work.

Although design should normally proceed downwards, some of the lowest level components may need to be designed (and coded) first. Examples are device drivers and utility libraries.

### 5.3.2     Production

5.3.2.1   Coding

When the design of each module is completed, reviewed and approved, it can be coded.

Coding conventions should be established and documented in the DDD. They should provide rules for:

- presentation, (e.g. header information and comment layout);

- naming programs, subprograms, files, variables and data;

- limiting the size of modules;

- using library routines, especially:

-     operating system routines;

-     commercial library routines (e.g. numerical analysis);

-     project specific utility routines;

- defining constants;

- using compiler specific features not in the language standard;

- error handling.

The standard header (see Part 2, Chapter 3) should be made available so that it can be edited, completed and then inserted at the head of each module.

Code should be consistent, as this reduces complexity. Rigorous adherence to coding conventions is fundamental to ensuring consistency.  Further, consistency is enhanced by adopting the same solutions to the same problems.  To preserve code consistency, changes and modifications should follow the style of the original code, assuming it was produced to recognised standards.

Code should be structured, as this reduces errors and enhances maintainability. Generally, this means resolving it into the basic sequence, selection (i.e. condition) and iteration (i.e. loop)s.  Practically, the ideas of structured programming require that:

- each module should have a single entry and exit point;

- control flow should proceed from the beginning to the end;

- related code should be blocked together rather than dispersed around the module;

- branching out of a module should only be performed under prescribed conditions (e.g. error exit).

Production of consistent, structured code is made easier by using tools such as language-sensitive editors, customised to suit the project conventions.

The coding process includes compilation; not only does this produce the object code needed for testing the run-time behaviour of a module, it is the first step in verifying the code.  Compilation normally produces statistics that can be used for the static analysis of the module.

Supplementary code included to assist the testing process should be readily identifiable and easy to disable, or remove, after successful testing. Care should be taken to ensure that such code does not obscure the module logic.

As the coding of a module proceeds, documentation of the design assumptions, function, structure, interface, internal data and resource utilisation should proceed concurrently.  This information should be recorded in Part 2 of the DDD.  The inclusion of this information in the source code is recommended.  To avoid the maintenance problem of having the same information in two places, tools to select information required for the DDD from the source code are desirable.

When a module has been documented and successfully compiled, unit testing can begin.

5.3.2.2   Integration

Integration is the process of building a software system by combining components into a working entity.

Integration of components should proceed in an orderly function-by-function sequence. This allows the software's operational capabilities to be demonstrated early, increasing management confidence that the project is progressing satisfactorily.

The integration process shall be controlled by the software configuration management procedures defined in the SCMP.  Good SCM procedures are essential for correct integration.

The top-down approach to integration is to use stubs to represent lower-level modules. As modules are completed and tested, they replace the stubs.  In many projects, the need to make shared components available at an early stage forces the integration to be organised initially on a bottom-up, and later on a top-down, basis. Whatever approach to integration  is taken, it should minimise the time spent in testing, while ensuring that all source statements are verified.

5.3.2.3   Testing

Procedures for developing and documenting the test approach are described in Part 2, Chapter 4.

5.3.2.3.1 Unit testing

Unit tests verify the design and implementation of all components from the lowest level defined in the detailed design up to the lowest level defined in the architectural design (normally the task level).  Modules that do not call other modules exist at the lowest level of the detailed design.

Unit tests verify that not only is a module doing what it is supposed to do (`black box' testing), but also that it is doing it in the way it was intended (`white box' testing). Before a module can be accepted, every statement shall be successfully executed at least once.  At a minimum, the most probable paths through a module should be identified and

tests designed to ensure these paths are executed. This type of `white box' testing is complementary to the black box approach.analysers and symbolic debuggers can be very useful in observing the internal behaviour of a module. For larger systems, ensure that modules are tested systematically.

Unit testing is normally carried out by the individuals or teams responsible for the components' production.

Unit test plans, test designs, test cases, test procedures and test reports are documented in the Unit Test section of the Software Verification and Validation Plan (SVVP/UT).

5.3.2.3.2 Integration testing

Integration testing is also done in the DD phase when the major components are assembled to build the system.  These major components are identified in the ADD.  Integration tests should be directed at verifying that major components interface correctly.  Integration testing should precede system testing and follow unit testing.

Integration testing shall check that all the data exchanged across an interface agree with the data structure specifications in the ADD. Integration testing shall confirm that the control flows defined in the ADD have been implemented.

Integration test designs, test cases, test procedures and test reports are documented in the Integration Test section of the Software Verification and Validation Plan (SVVP/IT).

5.3.2.3.3 System testing

System testing is the process of testing an integrated software system.  This testing can be done in the development or target environment, or a combination of the two.  System testing shall verify compliance with system objectives, as stated in the SRD.

System testing should include such activities as:

- passing data into the system, correctly processing and outputting it (i.e. end-to-end system tests);

- practice for acceptance tests (i.e. verification that user requirements will be met);

- stress tests (i.e. measurement of performance limits);

- preliminary estimation of reliability and maintainability;

- verification of the Software User Manual.

Trends in the occurrence of defects should be monitored in system tests;  the behaviour of such trends is important for the estimation of potential acceptability.

For most embedded systems, as well as systems using special peripherals, it is often useful or necessary to build simulators for the hardware with which the deliverable system will interface. Such simulators are often required because of:

- late availability of the final system hardware;

- low available test time with the final system hardware;

- desire to avoid damaging delicate and/or expensive hardware,  particularly flight hardware.

Simulators are normally a separate project in themselves. Effort should be made to ensure that they are available in time, and  that they are certified as identical, from an interface point of view, with the target hardware.

System test designs, test cases, test procedures and test reports are documented in the System Test section of the Software Verification and Validation Plan (SVVP/ST).

### 5.3.3     Reviews

The detailed design should be reviewed and agreed layer by layer as it is developed during the DD phase.  The design of any level invariably affects upper layers and a number of review cycles may be necessary before the design of a level can be finalised. Walkthroughs should be used to ensure that the detailed design is understood by all concerned. Inspections of the design, by qualified software engineers, should be used to reduce the occurrence of design defects.

When the detailed design of a major component is finished, a critical design review shall be convened to certify its readiness for implementation. The project leader should participate in these reviews, together with the team leader and team members concerned.

After modules have been coded and successfully compiled, walkthroughs or inspections should be held to verify that the implementation conforms to the design.

After production, the DD Review (DD/R) shall consider the reports of the verification activities and decide whether to transfer the software. This should be a technical review (see Part 2, Chapter 4). Review participants should include engineers, user representatives and managers.

## 5.4       OUTPUTS FROM THE PHASE

The main outputs of the phase are the code, DDD, SUM and the plans for the TR phase.

Progress reports, configuration status accounts, software verification reports and audit reports are also outputs of the phase. These should always be archived by the project.

### 5.4.1     Code

The developer should deliver all the items needed to execute and modify any part of the software produced in the project, e.g:

- source files;

- command procedure files;

- configuration management tools;

- source files for test software;

- test data;

- build and installation procedures.

All deliverable code shall be identified in a configuration item list.

### 5.4.2     Detailed Design Document

The DDD grows as the design proceeds to the lowest level of decomposition. Documentation should be produced concurrently with detailed design, coding and testing. In large projects, it may be convenient to organise the overall DDD into several volumes.  The DDD shall be an output of the DD phase.  A recommended table of contents

of the DDD is provided in Appendix C.

Part 1 of the DDD defines design and coding standards and tools, and should be prepared as the first activity of the DD phase, before work starts on detailed design and coding.

Part 2 of the DDD expands as the design develops.  Part 2 of the DDD shall have the same structure and identification scheme as the code itself, with a 1:1 correspondence between sections of the documentation and the software components.

The DDD shall be complete, accounting for all the software requirements in the SRD. A table cross-referencing software requirements to the detailed design components shall be placed in the DDD.

### 5.4.3     Software User Manual

A Software User Manual (SUM) shall be an output of the DD phase. The recommended table of contents for a SUM is provided in Appendix C. The rules for the style and content of the Software User Manual are based on ANSI/IEEE Std 1063-1987, `Software User Documentation'. Two styles of user documentation are useful: the `instruction', or `tutorial', style and the `reference' style. While the instruction style is oriented towards helping new users, the reference style is more suited  to more experienced users who need information about specific topics.

In the instruction section of the SUM, material is ordered according to the learning path, with the simplest, most necessary operations appearing first and more advanced, complicated operations appearing later. The size of this section depends on the intended readership; some users may understand the software after a few examples (and can switch to using the reference section) whilst other users may require many worked examples.

The reference section of the SUM presents the basic operations,or easy reference (e.g. alphabetically).  Reference documentation should be more formal, rigorous and exhaustive than the instructional section.  For example a command may be described in the instruction section in concrete terms, with a specific worked example. The description in the reference section should describe all the parameters, qualifiers and keywords, with several examples.

The development of the SUM should start as early as possible. Establishing the potential readership for the SUM should be the first step.  This information is critical for establishing the style of the document. Useful information may be found in the section `User Characteristics' in the URD.

The Software User Manual may be large, spread over several volumes.  The SUM may be made available electronically, for example as part of an online help facility.  There should be specific software requirements for such facilities.

### 5.4.4     Project management plan for the TR phase

The management plan for the TR phase must be documented in the DD phase section of the Software Project Management Plan (SPMP/TR, see Part 2, Chapter 2). This plan may also cover the period up to final acceptance.

### 5.4.5     Configuration management plan for the TR phase

The TR phase procedures for the configuration management of the deliverables, in the operational environment, must be documented in the Software Configuration Management Plan (SCMP/TR, see Part 2, Chapter 3).

### 5.4.6     Acceptance test specification

Acceptance test designs, test cases and test procedures must be documented in the Software Verification and Validation Plan (SVVP/AT, see Part 2, Chapter 4).

### 5.4.7     Quality assurance plan for the TR phase

The TR phase quality monitoring procedures must be defined in the TR phase section of the Software Quality Assurance Plan (SQAP/TR,2, Chapter 5).

# CHAPTER 6:  THE TRANSFER PHASE

## 6.1       INTRODUCTION

The TR phase can be called the `handover phase' of the life cycle. The purpose of the TR phase is to install the software in the operational environment and demonstrate to the initiator and users that the software has all the capabilities described in the User Requirements Document (URD).

Installation and checkout of the software is the responsibility of the developer.  Representatives of users and operations personnel shall participate in acceptance tests.   The Software Review Board (SRB) shall review the software's performance in the acceptance tests and recommend, to the initiator, whether the software can be provisionally accepted or not.

The principal output of this phase is the Software Transfer Document (STD), which documents the acceptance testing activities.

The TR phase terminates with provisional acceptance of the software and the start of operations.

## 6.2       INPUTS TO THE PHASE

The inputs to the TR phase are the:

- code;

- Detailed Design Document (DDD);

- Software User Manual (SUM);

- Acceptance Test specification (SVVP/AT).

- Software Project Management Plan for the TR phase (SPMP/TR);

- Software Configuration Management Plan for the TR phase  (SCMP/TR);

- Software Quality Assurance Plan for the TR phase (SQAP/TR).

## 6.3       ACTIVITIES

TR phase activities shall be carried out according to the plans defined in the DD phase.

### 6.3.1     Installation

The first activity of the TR phase is installation of the software.  This is done by:

- checking the deliverables against the configuration item list;

- building a system executable in the target environment.

Procedures for building software may vary, depending on the type of software, but the capability of building the system from the components that are directly modifiable by the maintenance team shall be established. Maintenance staff should exercise the procedures for modifying the software, especially if any unfamiliar software development tools have been supplied.

### 6.3.2     Acceptance tests

Acceptance tests validate the software, i.e. they demonstrate the capabilities of the software in its operational environment. Acceptance tests should be based on the user requirements, as stated in the URD. Acceptance tests plans, test designs, test cases and test procedures are defined in the SVVP. Acceptance tests are executed in the TR phase and the results recorded in the SVVP. A summary of the acceptance test reports should be inserted in the STD.

### 6.3.3     Provisional acceptance

Acceptance tests necessary for provisional acceptance shall be indicated in the SVVP.  The criterion for provisional acceptance is whether the software is ready for operational use.  A period of operations is usually required to show that the software meets all the requirements in the URD.

The provisional acceptance decision should be made by the initiator after consultations with the SRB, end-user representatives and operations staff.

## 6.4       OUTPUTS FROM THE PHASE

### 6.4.1     Statement of provisional acceptance

The statement of provisional acceptance shall be produced by the initiator, on behalf of the users, and sent to the developer.  Provisional acceptance marks the end of the TR phase.

### 6.4.2     Provisionally accepted software system

The provisionally accepted software system shall consist of the outputs of all previous phases and modifications found necessary in the TR phase.

### 6.4.3     Software Transfer Document

The purpose of the Software Transfer Document (STD) is to identify the software that is being transferred and how to build and install it. An output of the TR phase shall be the STD. The STD shall be handed over from the developer to the maintenance organisation at provisional acceptance.  The recommended table of contents for the STD is presented in Appendix C.

The STD shall contain a summary of the acceptance test reports and all documentation about software changes performed during the TR phase.

This page is intentionally left blank

# CHAPTER 7: THE OPERATIONS AND MAINTENANCE PHASE

## 7.1       INTRODUCTION

In the OM phase, the software first enters practical use. The operation of software is beyond the scope of these Standards, so this chapter only discusses maintenance.

The purpose of software maintenance is to ensure that the product continues to meet the real needs of the end-user. The available resources for maintenance should reflect the importance of the product.

Unlike hardware maintenance, which aims to return a hardware product to its original state, software maintenance always results in a change to a software product.  Software maintenance staff should thoroughly understand the software which they have to alter. Training may be necessary.

The principal output of this phase is the Project History Document (PHD), which summarises the development, operations and maintenance of the product.

## 7.2       INPUTS TO THE PHASE

The inputs to the OM phase are the:

- statement of provisional acceptance;

- provisionally accepted software system;

- Software Transfer Document.

## 7.3       ACTIVITIES

Until final acceptance, OM phase activities that involve the developer shall be carried out according to the plans defined in the SPMP/TR.

The maintenance organisation may choose to adopt the Software Configuration Management Plan used in the development phases. Alternatively they may choose to produce a new one, specific to their needs.  The effort to convert from one configuration management system  to another should not be underestimated, nor the risks involved ignored (e.g. the loss of configuration items or the incorrect attachment of labels).

The Software Project Management Plans and Software Quality Assurance Plans continue to apply to the activities of development staff, but not to operations and maintenance staff, who should develop their own plans.

### 7.3.1     Final Acceptance

The early part of the OM phase should include a warranty period in which the developer should retain responsibility for correcting errors.  The end of the warranty period is marked by final acceptance.

The criterion for final acceptance is whether the software meets all requirements stated in the URD. All the acceptance tests shall have been successfully completed before the software is finally accepted.

The final acceptance decision should be made by the initiator after consultations with the SRB, end-user representatives and operational staff. Even when no contractor is involved, there shall be a final acceptance milestone to arrange the formal handover from software development to maintenance.

Whenever the handover is performed, the last document formally released by  the engineering (as opposed to maintenance) project leader, must be the first issue of the Project History Document (PHD).

### 7.3.2     Maintenance

After this warranty period, maintenance of the software may be transferred from the developer to a dedicated maintenance organisation. A maintenance organisation shall be designated for every software product in operational use.  Resources shall be assigned to a product's maintenance until it is retired.

Maintenance of software should be driven by the occurrence of problems and new requirements.  The SRB controls problem handling activity, and shall authorise all modifications. Responsibility for minor modifications and emergency changes may be delegated to maintenance staff, depending on the level of criticality.

Procedures for software modification shall be defined.  This is normally done by carrying over the configuration management and verification procedures from the development phase.  Consistency between code and documentation shall be maintained.

Some software problems can give rise to new requirements.  A user, after experience with the software, may propose a modification (in an SPR). The SRB, classifying the problem as a new or changed requirement,  drafts changes to the URD and reviews it with the users concerned.  Users may also draft changes to the URD and put them forward to the SRB.

New requirements may also arise because the original requirements defined in the UR and SR phases were not appropriate, or because the user's needs change.  The maintenance budget should support a realistic level of requirement-change activity. Major new requirements should be handled as a separate software development project, and be separately budgeted.

Users should be kept informed of problems. If possible,items which are the subject of problem reports should be withdrawn from use while the problem is corrected. When withdrawal is not possible, temporary work-around solutions are permitted, provided the safety of the system is not impaired.  All software modifications must be documented, even temporary ones.

When software is changed, regression tests should be performed to ensure that the change has not caused new faults. Regression test cases may be a subset of the acceptance test cases.

## 7.4       OUTPUTS FROM THE PHASE

### 7.4.1     Statement of final acceptance

The statement of final acceptance shall be produced by the initiator, on behalf of the users, and sent to the developer.  Its delivery marks the formal handover of the software.  The precondition of final acceptance is that all the acceptance tests have been executed satisfactorily.

### 7.4.2     Project History Document

The Project History document (PHD) should be produced by the software project manager. It summarises the main events and outcome of the project. The PHD is useful to future projects for:

- estimating the effort required;

- setting up the  organisation;

- finding successful methods;

- advising about problems and pitfalls.

The PHD is the place where estimates, made in the planning stages, are compared with actual events.  The accuracy of predictions of the project schedule,  software volume, manpower requirements,requirements and cost should be measured.  Productivity should be estimated using the measurements of software volume, and time.

Preparation of the PHD forces a project manager to consider progress carefully, and to draw personal and organisational conclusions when the events concerned are fresh in the project manager's mind.  Accordingly, the project manager should start making notes for the PHD at the beginning of the project. At the end of each phase, the plans made for the previous phase should be compared with what actually happened.  This knowledge can also help in planning the next phase.

The PHD shall be delivered to the initiator after final acceptance, who should make it available to the maintenance organisation.  The chapter describing the performance of the system should be added by the designated maintenance organisation during the OM phase and updated when the product is retired. The recommended table of contents for the PHD is presented in Appendix C.

### 7.4.3     Finally accepted software system

This consists of one or more sets of documentation, source, object and executable code corresponding to the current versions and releases of the product.

# P a r t  2  P r o c e d u r e  S t a n d a r d s

Figure 1.1: Software Management Plans

# CHAPTER 1:  MANAGEMENT OF THE SOFTWARE LIFE CYCLE

## 1.1       INTRODUCTION

Part 2 of these standards describes the activities that are essential for managing the software life cycle.  Whereas Part 1 describes the activities and products of each phase of the life cycle, Part 2 discusses management activities which are performed throughout all development phases.

The goal of the management activities is to build the product within budget, according to schedule, with the required quality. To achieve this, plans must be established for:

- software project management;

- software configuration management;

- software verification and validation;

- software quality assurance.

Figure 1.1 summarises how these plans must be documented. Plans for project management, configuration management, verification,n and quality assurance are split into sections. Each section plans the activities for subsequent phases. While the same structure may be repeated in each section of a document, the actual contents may vary.  Titles of documents are separated from their section names by `/' (e.g. SPMP/SR is the SR phase section of the Software Project Management Plan).

Figure 1.1 does not include the plans required to manage the maintenance of the software in the period between final acceptance and retirement. The maintenance organisation may choose to reuse development plans or produce new plans.

## 1.2       SOFTWARE PROJECT MANAGEMENT

A project manager, or project management team, has to plan, staff, monitor, control and lead a software project.  The project manager is responsible for writing the Software Project Management

Plan (SPMP). The project manager leads the development team and is

the principal point of contact between them and the initiator,

end-users and other parties.

## 1.3       SOFTWARE CONFIGURATION MANAGEMENT

Proper configuration management is essential for control of a software product.  A component may function perfectly well, but either a fault in integration or a mistake in identification can result in obscure errors. This standard defines requirements for identifying, controlling, releasing and changing software items and recording their status. Procedures for managing the software configuration must be defined in the Software Configuration Management Plan (SCMP).

## 1.4       SOFTWARE VERIFICATION AND VALIDATION

These standards adopt the general ANSI/IEEE definition of verification as the process of reviewing, inspecting, testing, auditing and reviewing the software products. Verification is essential to assure that the product will be fit for its purpose.

The verification approach should be planned by project management and carried out by development staff.

In these standards, `validation' is the evaluation of software at the end of the development process to ensure compliance with user requirements.  Validation is done in the TR phase.

All verification and validation activities must be documented in the Software Verification and Validation Plan (SVVP).

## 1.5       SOFTWARE QUALITY ASSURANCE

The quality assurance activity is the process of verifying that these standards are being applied.  In small projects this is done by the project manager, but in large projects specific staff should be allocated to the role.  The Software Quality Assurance Plan is the document which describes how adherence to the Standards is to be verified.

Where ESA PSS-01-series documents are applicable, and as a consequence ESA PSS-01-21, `Software Product Assurance Requirements for ESA Space Systems' is also applicable, Part 2, Chapter 5 of these Standards, `Software Quality Assurance', ceases to apply.

# CHAPTER 2: SOFTWARE PROJECT MANAGEMENT

## 2.1       INTRODUCTION

Software Project Management (SPM) is `the process of planning, organising, staffing, monitoring, controlling and leading a software project' (ANSI/IEEE Std 1058.1-1987). The Software Project Management Plan (SPMP) is the controlling document for managing a software project. The SPMP defines the technical and managerial project functions, activities and tasks necessary to satisfy the requirements of a software project.

The SPMP is updated and refined, throughout the life cycle, as more accurate estimates of the effort involved become possible, and whenever changes in requirements or design occur. A number of methods and tools are available for software project planning and their use is recommended.

During all the phases of the life cycle, project management should review how a plan works out in practice.  Important deviations between estimates and actuals have to be explained and documented in the Project History Document (PHD), which is issued in the OM phase.

## 2.2       ACTIVITIES

### 2.2.1     Organising the project

A key responsibility of software project management is organising all project activities. There are several possible models for the organisation of a software project (e.g. functional and matrix).

Once tasks have been defined, project management must define the team structure to carry them out. Positions in that structure should be adequately defined so that each team member has clear responsibilities and lines of authority. These responsibilities should be documented in terms of reference and work package descriptions.

### 2.2.2     Leading the project

Project management decide the objectives and priorities at each stage. They should document the assumptions, dependencies and constraints that influence their decisions in the SPMP.

### 2.2.3     Risk management

Risks threaten a project's success. Project management should identify the risks to a project and assess the threat they pose. This is called `risk analysis'.  Examples of potential risk areas are:

- quality and stability of user requirements;

- level of definition and stability of external interfaces;

- adequacy and availability of resources;

- availability and quality of tools;

- staff training and experience;

- definition of responsibilities;

- short time scales;

- technical novelty of the project.

Project management should devise a plan for reducing risk levels and ensure that it is carried out. Achievements should be measured and the risks reevaluated throughout the project.

Decisions about priorities should be supported by risk analysis. Accurate assessment of the impact of decisions relies on quantitative estimation of the factors that should change when action is taken.

### 2.2.4     Technical management

There are many methods and tools that can be applied throughout the software life cycle, which can greatly enhance the quality of the end product and their use is strongly recommended.  Project management is responsible for selecting methods and tools, and for enforcing their use.

Technical management includes organising software configuration management, and verification, validation and test activities.

### 2.2.5     Planning, scheduling and budgeting the work

Estimating the resources and time scales required for activities is a key part of planning their execution. The basic approach to estimation is to analyse the project into tasks that are small enough for their costs to be evaluated easily and accurately. Estimates for the time scales and resources for the whole project are then synthesised from the estimates for the individual tasks. Each task should be linked to an appropriate part of the deliverable for that phase.  For example,  tasks in the SR phase might be based on requirements, whereas in the AD phase they might be based on components.  Traditionally, estimates for detailed design and production have been based on lines of code.

Other factors that affect estimates are the experience of the development team, the novelty of the technical area and the availability of software engineering tools.

The Work Breakdown Structure (WBS) is one of the fundamental tools for the planning and control of project activities. The WBS describes the hierarchy of tasks (grouped into `work packages') to be carried out in a project. The WBS corresponds to the structure of the work to be performed, and reflects the way in which the project costs will be summarised and reported.

A work package defines a set of tasks to be performed in a project.  Work package descriptions should define tasks in sufficient detail to allow individuals, or small groups of people, to work independently of the rest of the project.  The start and end dates of a work package should be specified. The duration of a product oriented work package should be sufficiently short to maintain visibility of the production process (e.g. a month in the DD phase).

Procedure-oriented work packages, for example project management, may extend over the entire length of the project.

The work schedule  should show when the work packages are to be started and finished.  A milestone chart shows key events in the project; these should be related to work package completion dates.

An estimate of the cost of the whole project should be included in the SR phase section of the SPMP. Pending definition of the software requirements and the design, it will be difficult to provide accurate estimates. The actual costs of similar projects help in making initial estimates.

Cost models may be used for estimating the time required for detailed design and production. Careful consideration should be given to the applicability of any cost model.  Parameter values attributed in making a cost model estimate should be clearly documented.

### 2.2.6     Reporting project progress

Project reporting is essential for the proper control of a software project.  Carried out by project management, it provides visibility of development activity at regular intervals during the project. Reports are necessary to assure people outside the development team that the project is proceeding satisfactorily.

Project management should ensure that material presented at progress reviews is sufficiently detailed, and in a consistent format that enables the PHD to be compiled simply from progress-review data.

Contracts for software procurement should require that progress data be collected and progress reports be generated during the development.  When it is necessary to keep information confidential between ESA and the contractor, the progress reports  and PHD may be marked `For ESA use only'.

## 2.3       THE SOFTWARE PROJECT MANAGEMENT PLAN

All software project management activities shall be documented in the Software Project Management Plan (SPMP). The SPMP is the controlling document for managing a software project. The SPMP is divided into four sections which contain the management plans for the SR, AD, DD and TR phases.  The table of contents for each section of the SPMP is described in Appendix C. This table of contents is derived from the IEEE Standard for Software Project Management Plans (IEEE Std 1058.1-1987).

## 2.4       EVOLUTION OF THE SPMP THROUGHOUT THE LIFE CYCLE

### 2.4.1     UR phase

By the end of the UR review, the SR phase section of the SPMP shall be produced (SPMP/SR). The SPMP/SR describes, in detail, the project activities to be carried out in the SR phase. As part of its introduction, the SPMP/SR shall outline a plan for the whole project.

A rough estimate of the total cost of the software project should be included in the SPMP/SR. Technical knowledge and experience gained on similar projects should be used in arriving at the cost estimate.

A precise estimate of the effort involved in the SR phase shall be included in the SPMP/SR. Specific factors affecting estimates for the work required in the SR phase are the:

- number of user requirements;

- level of user requirements;

- stability of user requirements;

- level of definition of external interfaces;

- quality of the URD.

An estimate based simply on the number of user requirements might be very misleading - a large number of detailed low-level user requirements might be more useful, and save more time in the SR phase, than a few high-level user requirements. A poor quality URD might imply that a lot of requirements analysis is required in the SR phase.

### 2.4.2     SR phase

During the SR phase, the AD phase section of the SPMP shall be produced (SPMP/AD).  The SPMP/AD describes, in detail, the project activities to be carried out in the AD phase.

An estimate of the total project cost shall be included in the SPMP/AD. Every effort should be made to arrive at estimates with an accuracy better than 30%. Technical knowledge and experience gained on similar projects should be used in arriving at an estimate of the total project cost.

When no similar projects exist, it may be useful to build a prototype, to get a more precise idea of the complexity of the software. Prototyping activities should be properly planned and resourced.

A precise estimate of the effort involved in the AD phase shall be included in the SPMP/AD. Specific factors that affect estimates for the work required in the AD phase are:

- number of software requirements;

- level of software requirements;

- stability of software requirements;

- level of definition of external interfaces;

- quality of the SRD.

If an evolutionary development life cycle approach is to be used, then this should be stated in the SPMP/AD.

### 2.4.3     AD phase

During the AD phase, the DD phase section of the SPMP shall be produced (SPMP/DD). The SPMP/DD describes, in detail, the project activities to be carried out in the DD phase.

An estimate of the total project cost shall be included in the SPMP/DD.  An accuracy of 10% should be aimed at. The number of lines of code should be estimated for each software component. This should be used to estimate the time required to write the software, and therefore its cost.

The SPMP/DD shall contain a WBS that is directly related to the decomposition of the software into components.

The SPMP/DD shall contain a planning network showing relationships of coding, integration and testing activities. Tools are available for this kind of planning.

### 2.4.4     DD phase

As the detailed design work proceeds to lower levels, the WBS and job schedule need to be refined to reflect this. To achieve the   necessary level of visibility, no software production work packages

in the SPMP/DD shall last longer than 1 man-month.

During the DD phase, the TR phase section of the SPMP shall be produced (SPMP/TR). The SPMP/TR describes, in detail, project  activities until final acceptance, in the OM phase.

# CHAPTER 3: SOFTWARE CONFIGURATION MANAGEMENT

## 3.1       INTRODUCTION

As defined in ANSI/IEEE Std 729-1983, software configuration management (SCM) is the :

- process of identifying and defining the configuration items in a system;

- controlling the release and change of these items throughout the system life cycle;

- recording and reporting the status of configuration items and change requests;

- verifying the completeness and correctness of configuration items.

Software configuration management is both a managerial and a technical activity, and is essential for proper software quality control. The software configuration management activities for a project must be defined in the Software Configuration Management Plan (SCMP).

All software items, for example documentation, source code, executable code, files, tools, test software and data, shall be subjected to configuration management procedures.  The configuration management procedures shall establish methods for identifying,nd changing software items through development, integration and transfer.  In large developments, spread across multiple hardware platforms, configuration management procedures may differ in physical details. However, a common set of configuration management procedures shall be used.

Tools for software configuration management are widely available. Their use is strongly recommended to ensure that SCM procedures are applied consistently and efficiently.

## 3.2       ACTIVITIES

### 3.2.1     Configuration identification

A `configuration item' (CI) is a collection of software elements, treated as a unit, for the purpose of configuration management. Several  factors may be relevant in deciding where to draw the boundaries of a configuration item. A configuration item may be any kind of software item, for example: a module, a document, or a set of CIs.

The key to effective software configuration management is unambiguous identification of the parts of the software. Every configuration item shall have an identifier that distinguishes it from other items with different:

- requirements, especially functionality and interfaces;

- implementation.

Each component defined in the design process shall be designated as a CI and possess an identifier.  The identifier shall include a number or a name related to the purpose of the CI.  The identifier shall include an indication of the type of processing the CI is intended for (e.g. filetype information).

The term `version' is used to define a stage in the evolution of a CI.  Each stage is marked by a `version number'.  When the CI changes, the version number changes.  The identifier of a CI shall include a version number.

The identifier of documents shall include an issue number and a revision number.  Issue numbers are used to mark major changes and revision numbers are used to mark minor changes.  Major changes usually require formal approval. The issue number and revision number together mark the version of the document.

The configuration identification method shall be capable of accommodating new CIs, without requiring the modification of the identifiers of any existing CIs.

A `baseline' is a document or a product that has been formally reviewed and agreed upon, and is a basis for further development. A baseline is an assembly of configuration items. Formal change control procedures are required to modify a baseline.

Integration of software should be coordinated by the identification and control of baselines.  Figure 3.2.1 illustrates the relationship between units of modules, baselines and releases.

Modules, after successful unit testing, are integrated into existing baselines. Incorporation into a baseline can only occur after successful integration tests.  Baselines must be system tested before being transferred to users as a `release' of the software. After delivery and installation, releases of the software undergo acceptance testing by users.

Figure 3.2.1: Baselines and releases

(Available only in hard copy)

In the TR phase, a list of configuration items in the first release shall be included in the STD. In the OM phase, a list of changed configuration items shall be included in each Software Release Note (SRN). An SRN shall accompany each release made in the OM phase.

As part of the configuration identification method, a module shall have a header that includes:

- configuration item identifier (name, type, version);

- original author;

- creation date;

- change history (version/date/author/description);

Note that a module header may also contain other component information from the DDD, Part 2.

All documentation and storage media shall be clearly labelled in a standard format, with at least the following data:

- project name;

- configuration item identifier (name, type, version);

- date;

- content description.

### 3.2.2     Configuration item storage

A software library is a controlled collection of configuration items.  It may be a single file or a collection of files.  A library may exist on various media (e.g. paper, magnetic disk).

To ensure the security and control of the software, as a minimum, the following software libraries shall be implemented for storing all the deliverable components (e.g. documentation, source and executable code, test files, command procedures):

- Development (or Dynamic) library;

- Master (or Controlled) library;

- Static (or Archive) library.

Tools for handling software libraries are essential for efficient configuration control.  Such tools should allow CI identification, change tracking, and CI cross-referencing.

Software is coded and tested as a set of modules in the development library. After unit tests, modules are transferred to master libraries for integration testing and system testing. When changes to master library modules are necessary, the appropriate modules are transferred back to a development library from the master library.

A baseline includes a set of master libraries. When a baseline is released, copies of all master libraries should be taken. These copies, called `static' libraries, shall not be modified.

Up-to-date security copies of master and static libraries shall always be available.  Procedures for the regular backup of development libraries shall be established.  This is called `media control'.

### 3.2.3     Configuration change control

Software configuration control is the process of evaluating proposed changes to configuration items and coordinating the implementation of approved changes.  Software configuration control of an item can only occur after formal establishment of its configuration identification and inclusion in a baseline.  Proper software configuration control demands the definition of:

- the level of authority required to change each CI;

- the methods for handling proposals for changing any CI.

At the top level, the software configuration control process  identifies the procedures for handling changes to known baselines.

In addition, project management has the responsibility for the organisation of SCM activities, the definition of SCM roles (e.g.tion control board and software librarian), and the allocation of staff to those roles.  In the TR and OM phases of a software project, ultimate responsibility for software configuration control lies with the Software Review Board (SRB).  The SRB should be composed of members with sufficient authority and expertise to resolve any problems or nonconformances of the software.

When a software item does not conform to its specification, it should be identified as non-conforming, and held for review action.

Nonconformance should be classified as minor or major depending on its severity and by its urgency. Minor nonconformances can be processed at a level below SRB. Depending on the size and the management structure of the  software development, a further classification should be performed in relation to the software life cycle, i.e. against the user requirements, software requirements,tc.

Changes to external interfaces or to software packages used by the system should be handled like changes to ordinary CIs.

3.2.3.1   Levels of change control

As a configuration item passes through unit, integration, system and acceptance tests, a higher level of authority is needed to approve changes.  This is called the promotion of a CI. Just as programmers sign off unit tests, team leaders sign off integration tests, and project leaders sign off system tests, so change approval demands a level of authority corresponding to the verification status of the CI.

3.2.3.2   Change control procedures

Changes occur naturally in the evolution of the software system. This evolution should be planned and implemented using controlled software libraries.  Changes can also occur because of problems in development or operation.  Such changes require backtracking through the life cycle to ensure that the corrections are carried out with the same degree of quality control as was used for the original development. The level of authority for each change depends on the part to be changed, and on the phase in the life cycle that has been reached.

3.2.3.2.1 Documentation change procedures

The change procedure described below shall be observed when changes are needed to a delivered document.

1.    A draft of a document is produced and submitted for review. If  the document is not new, all changed text must be identified.

2.    The reviewers record their comments about the draft document on RID forms. A recommended solution may be inserted on the RID form. The RIDs are then returned to the author(s) of the document.

3.    The author(s) of the document record their response on the RID form.

4.    Each RID is processed at a formal review meeting and an action decided (see Section 4.2.1).

5.    The draft document and the approved  RIDs are used to make the next revision, or issue if there major changes, of the document.

6.    Each revision or issue of a document must be accompanied by a Document Change Record (DCR) and an updated Document Status Sheet (DSS).

Up to the end of the TR phase, the formal review meeting is a UR/R, SR/R, AD/R or DD/R, depending on the document.  In the OM phase the formal review is conducted by the SRB. Templates for RID, DCR and DSS forms are provided in Appendix E.

3.2.3.2.2 Problem reporting procedures

Software problems can be reported at any stage in the life cycle. Problems can fall into a number of categories according to the degree of regression in the life cycle.

Problem categories are:

- operations error;

- user documentation does not conform to code;

- code does not conform to design;

- design does not conform to requirements;

- new or changed requirements.

Selection of the problem category defines the phase of the life cycle at which corrective action needs to start.

Software problems and change proposals shall be handled by the procedure described below.  This change procedure requires a formal review to be held (see Section 4.2.1).

- A Software Problem Report (SPR) must be completed for each detected problem, giving all information about the symptoms, the operating environment and the software under test.  Evidence, such as listings of results, may be attached. A problem does not formally exist until an SPR has been written.

- The SPR is passed to the Software Review Board (SRB) who will assign it to the relevant authority for analysis. A Software Change Request form (SCR) must be completed for each software change found necessary. This describes the changes required and includes an assessment of the cost and schedule impacts.

- The Software Review Board then reviews each SCR and, if appropriate, assigns someone to carry out the change.

- Each software modification is documented in detail in a Software Modification Report (SMR), complete with items such as:

- source code changes;

- test reports;

- documentation changes;

- verification reports.

Templates of SPR, SCR and SMR forms are given in Appendix E.

### 3.2.4     Configuration status accounting

Software configuration status accounting is the administrative tracking and reporting of all configuration items.

The status of all configuration items shall be recorded.

Configuration status accounting continues, as do all other configuration management activities, throughout the life cycle.

To perform software status accounting, each software project shall record the:

- date and version/issue of each baseline;

- date and status of each RID and DCR;

- date and status of each SPR, SCR and SMR;

- summary description of each Configuration Item.

Configuration status accounts should be produced at project milestones, and may be produced periodically between project milestones.

Information in configuration status accounts should be used to generate the SRNs and CI lists that must accompany each delivery of a software baseline.

### 3.2.5     Release

The first release of the software must be documented in the STD. Subsequent releases of software must be accompanied by a Software Release Note (SRN) that lists the CIs included in the release, and the procedures for installing them, so that they can made available for use (see Appendix E). As a minimum, the SRN shall record the faults that have been repaired and the new requirements that have been incorporated.

For each release, documentation and code shall be consistent.old releases shall be retained, for reference.  Where possible, the previous release should be kept online during a change-over period, to allow comparisons, and as a fallback. Older releases may be archived.  The number of releases in operational use at any time should be minimised.

Some form of software protection is desirable for controlled source and binary code to avoid use of an incorrect release. The strength of this protection depends on the criticality of use of the product. In general, each release should be self-identifying (e.g. operator dialogue or printed output).

Modified software shall be retested before release.  Tests should be selected from the SVVP to demonstrate its operational capability.

While it is usually not necessary to repeat all the acceptance tests after a software change is made, a standard subset of the acceptance tests (often called `regression tests') should be run when any new release is made. These tests are required to demonstrate that a modification has introduced no unexpected side effects.

## 3.3       THE SOFTWARE CONFIGURATION MANAGEMENT PLAN

All software configuration management activities shall be documented in the Software Configuration Management Plan (SCMP). The SCMP is divided into four sections which contain the configuration management plans for the SR, AD, DD and TR phases.  The table of contents for each section of SCMP is described in Appendix C.  This

table of contents is derived from the IEEE Standard for Software Configuration Management Plans (ANSI/IEEE Std 828-1983).

Additional information on configuration management may be found in ANSI/IEEE Std 1042-1987, Guide to Software Configuration Management.

## 3.4       EVOLUTION OF THE SCMP THROUGHOUT THE LIFE CYCLE

Configuration management procedures shall be in place before software production (code and documentation) starts. SCM procedures should be simple and efficient. Wherever possible, procedures should be capable of reuse in later phases. Instability in SCM procedures can be a major cause of poor progress in a software project.

### 3.4.1     UR phase

By the end of the UR review, the SR phase section of the SCMP shall be produced (SCMP/SR). The SCMP/SR shall cover the configuration management procedures for all documentation, CASE tool outputs or prototype code, to be produced in the SR phase.

### 3.4.2     SR phase

During the SR phase, the AD phase section of the SCMP shall be produced (SCMP/AD). The SCMP/AD shall cover the configuration management procedures for documentation, CASE tool outputs or prototype code, to be produced in the AD phase. Unless there is a good reason to change (e.g. different CASE tool used), SR phase procedures should be reused.

### 3.4.3     AD phase

During the AD phase, the DD phase section of the SCMP shall be produced (SCMP/DD). The SCMP/DD shall cover the configuration management procedures for documentation, deliverable code, CASE tool outputs or prototype code, to be produced in the  DD phase. Unless there is a good reason to change, AD or SR phase procedures should be reused.

### 3.4.4     DD phase

During the DD phase, the TR phase section of the SCMP shall be produced (SCMP/TR). The SCMP/TR shall cover the procedures for the configuration management of the deliverables in the operational environment.

# CHAPTER 4:  SOFTWARE VERIFICATION AND VALIDATION

4.1       INTRODUCTION

In ANSI/IEEE Std 729-1983, three definitions of verification are given.  Verification can mean the:

- act of reviewing, inspecting, testing, checking, auditing, or otherwise establishing and documenting whether or not items, processes, services or documents conform to specified requirements (ANSI/ASQC A3-1978);

- process of determining whether or not the products of a given phase of the software development life cycle fulfil the requirements established during the previous phase;

- formal proof of program correctness.

The first definition of verification in the list above is the most general and includes the other two.  In these Standards, the first definition (ANSI/ASQC A3-1978) applies.

Validation is, according to its ANSI/IEEE definition, `the evaluation of software at the end of the software development process to ensure compliance with the user requirements'.  Validation is,, `end-to-end' verification.

Verification is essential for assuring the quality of a product. Software verification is both a managerial and a technical function, since the verification programme needs to be both defined and implemented. A project's verification activities should reflect the software's criticality, and the quality required of it.

Verification can be the most time-consuming and expensive part of a project; verification activities should appear in the SPMP. Figure 4.1 shows the life cycle verification approach.

Figure 4.1 Life cycle verification approach

(Available only on hard copy)

## 4.2       ACTIVITIES

Verification activities include:

- technical reviews, walkthroughs and software inspections;

- checking that software requirements are traceable to user requirements;

- checking that design components are traceable to software requirements;

- checking formal proofs and algorithms;

- unit testing;

- integration testing;

- system testing;

- acceptance testing;

- audits.

The actual activities to be conducted in a project are described in the Software Verification and Validation Plan (SVVP).

As well as demonstrating that assertions about the software are true, verification can also show that assertions are false.  The skill and ingenuity needed to identify defects should not be underestimated.  Users will have more confidence in a product that has been through a rigorous verification programme than one subjected to minimal examination and testing before release.

### 4.2.1     Reviews

The procedures for software reviews are based closely on the ANSI/IEEE Std 1028-1988.  A software review is an evaluation of a software element to ascertain discrepancies from planned results and to recommend improvements.

Three kinds of reviews can be used for software verification:

- technical review;

- walkthrough;

- software inspection.

The three kinds of reviews are all `formal reviews' in the sense that all have specific objectives and procedures.  All kinds of review seek to identify defects and discrepancies of the software against specifications, plans and standards.

The software problem reporting procedure and document change procedure defined in Part 2, Section 3.2.3.2, call for a formal review process for all changes to code and documentation.  Any of the three kinds of formal review procedure can be applied for change  control.  The SRB, for example, may choose to perform a technical review, software inspection or walkthrough as necessary.

4.2.1.1   Technical reviews

Technical reviews should be used for the UR/R, SR/R, AD/R, and DD/R. Technical reviews evaluate specific software elements to verify progress against plan.

The objective of a technical review is to evaluate a specific software element (e.g. document, source module), and provide management with evidence that:

- it conforms to specifications made in previous phases;

- the software element has been produced according to the project standards and procedures;

- changes have been properly implemented, and affect only those systems areas identified by the change specification (described in a DCR or SCR).

4.2.1.2   Walkthroughs

Walkthroughs should be used for the early evaluation of documents, models, designs and code in the SR, AD and DD phases.

The objective of a walkthrough is to evaluate a specific software element (e.g. document, source module).  A walkthrough should attempt to identify defects and consider possible solutions.

In contrast with other forms of review, secondary objectives are to educate, and to resolve stylistic problems.

4.2.1.3   Software inspections

Software inspections should be used for the evaluation of documents and code in the SR, AD and DD phases, before technical review or testing.

The objective of a software inspection is to detect and identify defects. A software inspection is a rigorous peer examination that:

- identifies nonconformances with respect to specifications and standards;

- uses metrics to monitor progress;

- ignores stylistic issues;

- does not discuss solutions.

### 4.2.2     Tracing

Forwards traceability requires that each input to a phase shall be traceable to an output of that phase. Forwards traceability demonstrates completeness. Forwards tracing is normally done by constructing cross-reference matrices. Holes in the matrix demonstrate incompleteness quite vividly.

Backwards traceability requires that each output of a phase shall be traceable to an input to that phase. Outputs that cannot be traced to inputs are superfluous, unless it is acknowledged that the inputs themselves were incomplete. Backwards tracing is normally done by including with each item a statement of why it exists (e.g. the description of the function of a component may be a list of functional requirements).

During the software life cycle it is necessary to trace:

- user requirements to software requirements and vice-versa;

- software requirements to component descriptions and vice versa;

- integration tests to major components of the architecture and

- vice-versa;

- system tests to software requirements and vice-versa;

- acceptance tests to user requirements and vice-versa.

To support traceability, all components and requirements are identified.  The SVVP should define how tracing is to be done.

References to components and requirements should include identifiers.

### 4.2.3     Formal proof

Where practical, formal deductive proof of the correctness of software may be attempted.

Formal Methods, such as Z and VDM, possess an agreed notation, with well-defined semantics, and a calculus, which allows proofs to be constructed. The first property is shared with other methods for software specification, but the second sets them apart.  If a Formal Method can demonstrate with certainty that something is correct, then separate verification is not necessary.  However, human errors are still possible, and ways should be sought to avoid this, for example by ensuring that all proofs are checked independently.

Refinement of a formal specification into executable code is generally not a deductive process; other forms of verification (e.g. testing), are necessary to verify the refinement.

### 4.2.4     Testing

Testing is the process of exercising or evaluating a system or system component, by manual or automated means, to:

- confirm that it satisfies specified requirements;

- identify differences between expected and actual results.

The amount of time spent in testing software is frequently underestimated. Testing activities must be carefully specified so that they can be adequately budgeted for.  The expense of testing increases with the number of errors present before it begins. Cheaper methods of removing errors, such as inspection, walkthrough and formal proof, should always be tried before testing is started.

Software testing includes the following activities:

- planning the general approach and allocating resources;

- detailing the general approach for various kinds of tests in a test design;

- defining the inputs, predicted results and execution conditions in a test case specification;

- stating the sequence of actions to be carried out by test personnel in a test procedure;

- logging the execution of a test procedure in a test report.

Four kinds of testing have been identified in these Standards:   unit testing, integration testing, system testing and acceptance  testing.

Test software should be produced to the same standards as the    deliverable software. Test software and data must therefore be   documented and subjected to configuration control procedures.  This   allows monitoring of the testing process, and permits test software   and data to be reused later, to verify that the software's   functionality and performance have not been impaired by  modifications.  This is called `regression' testing.

Test plans, test designs, test cases, test procedures and test  reports for unit, integration, system and acceptance tests must be  documented in the SVVP. Figure 4.2.4 summarises when and where  testing is documented in the SVVP.

In Figure 4.2.4, the entry `Plans' in the System Tests row, for example, means that the System Test Plans are drawn up in the SR  phase and placed in the SVVP section `System Tests', subsection `Plans'.  This is abbreviated as `SVVP/ST/Plans'.

Reports of Acceptance Tests must also be summarised in the Software Transfer Document.

Figure 4.2.4 Life cycle production of test documentation

(Available only on hard copy)

### 4.2.5     Auditing

Audits are independent reviews that assess compliance with software requirements, specifications, baselines, standards,s, instructions, codes and contractual and licensing requirements.  A `physical audit' checks that all items identified as being part of the configuration are present in the product baseline.

A `functional audit' checks that unit, integration and system tests have been carried out and records their success or failure.

Functional  and physical audits shall be performed before the release of the software.

## 4.3       THE SOFTWARE VERIFICATION AND VALIDATION PLAN

All software verification and validation activities shall be documented in the Software Verification and Validation Plan (SVVP).

The SVVP is divided into seven sections which contain the verification plans for the SR, AD, DD phases and the unit, integration, system and acceptance test specifications.  The table of contents for each section of SVVP is described in Appendix C.  This table of contents is derived from the IEEE Standard for Verification and Validation Plans (IEEE Std 1012-1989) and the IEEE Standard for Software Test Documentation (IEEE Std 829-1983).

The SVVP shall ensure that the verification activities:

- are appropriate for the degree of criticality of the software;

- meet the verification and acceptance testing requirements (stated in the SRD);

- verify that the product will meet the quality, reliability, maintainability and safety requirements (stated in the SRD);

- are sufficient to assure the quality of the product.

## 4.4       EVOLUTION OF THE SVVP THROUGHOUT THE LIFE CYCLE

### 4.4.1     UR phase

By the end of the UR review, the SR phase section of the SVVP shall be produced (SVVP/SR). The SVVP/SR shall define how to trace user requirements to software requirements, so that each software requirement can be justified. It should describe how the SRD is to be evaluated by defining the review procedures. It may include specifications of the tests to be performed with prototypes.

The initiator(s) of the user requirements should lay down the principles upon which the acceptance tests should be based.  The developer shall construct an acceptance test plan in the UR phase and document it in the SVVP. This plan should define the scope, approach, and schedule of acceptance testing activities.

### 4.4.2     SR phase

During the SR phase, the AD phase section of the SVVP shall be produced (SVVP/AD).  The SVVP/AD shall define how to trace software requirements to components, so that each software component can be justified. It should describe how the ADD is to be evaluated by defining the review procedures. It may include specifications of the

tests to be performed with prototypes.

During the SR Phase, the developer analyses the user requirements and may insert `Acceptance testing requirements' in the SRD.  These requirements constrain the design of the acceptance tests. This must be recognised in the statement of the purpose and scope of the acceptance tests.

The planning of the system tests should proceed in parallel with the definition of the software requirements.  The developer may identify `Verification requirements' for the software - these are additional constraints on the unit, integration and system testing activities. These requirements are also stated in the SRD.

The developer shall construct a system test plan in the SR phase and document it in the SVVP.  This plan should define the scope, approach, resources and schedule of system testing activities.

### 4.4.3     AD phase

During the AD phase, the DD phase section of the SVVP shall be produced (SVVP/DD). The SVVP/AD shall describe how the DDD and code are to be evaluated by defining the review and traceability procedures.

The developer shall construct an integration test plan in the AD phase and document it in the SVVP.  This plan should describe the scope, approach, resources and schedule of intended integration tests.  Note that the items to be integrated are the software components described in the ADD.

### 4.4.4     DD phase

In the DD phase, the SVVP sections on testing are developed as the detailed design and implementation information become available.

The developer shall construct a unit test plan in the DD phase and document it in the SVVP.  This plan should describe the scope, resources and schedule of intended unit tests.  The items to be tested are the software components described in the DDD.

The unit, integration, system and acceptance test designs shall be described in the SVVP. These should specify the details  of the test approach for a software feature, or combination of software features, and identify the associated tests.

The unit integration, system and acceptance test cases shall be described in the SVVP. These should specify the inputs, predicted results and execution conditions for a test item.

The unit, integration, system and acceptance test procedures shall be described in the SVVP. These should be provide a step-by-step description of how to carry out each test case.

The unit, integration, system and acceptance test reports shall be contained in the SVVP.

# CHAPTER 5:  SOFTWARE QUALITY ASSURANCE

NOTE: Where ESA PSS-01-series documents are applicable, and as a consequence ESA PSS-01-21, `Software Product Assurance Requirements for ESA Space Systems' is also applicable, this chapter ceases to apply.

## 5.1       INTRODUCTION

Software Quality Assurance (SQA) is `a planned and systematic pattern of all actions necessary to provide adequate confidence that the item or product conforms to established technical requirements' (ANSI/IEEE Std 730.1-1989). Software Quality Assurance is synonymous with Software `Product Assurance' (PA) and the terms are used interchangeably in these Standards.

The quality assurance activity is the process of verifying that these standards are being applied.  In small projects this could be done by the development team, but in large projects specific staff should be allocated to the role.

The Software Quality Assurance Plan (SQAP) defines how adherence to these standards will be monitored.  The SQAP contents list is a checklist for activities that have to be carried out to assure the quality of the product. For each activity, those with responsibility for SQA should describe the plans for monitoring it.

## 5.2       ACTIVITIES

Objective evidence of adherence to these standards should be sought during all phases of the life cycle.  Documents called for by this standard should be obtained and examined. Source code should be checked for adherence to coding standards. Where possible, aspects of quality (e.g. complexity, reliability, maintainability, safety, defects, number of problems, number of RIDs) should be  measured quantitatively, using well-established metrics.

Subsequent sections list activities derived from ANSI/IEEE Std 730.1-1989 that are necessary if a software item is to be fit for its purpose. Each section discusses how the activity can be verified.

### 5.2.1     Management

Analysis of the managerial structure that influences and controls the quality of the software is an SQA activity.  The existence of an appropriate organisational structure should be verified.  It should be confirmed that the individuals defined in that structure have defined tasks and responsibilities.  The organisation, tasks and responsibilities will have been defined in the SPMP.

### 5.2.2     Documentation

The documentation plan that has been defined in the SPMP should be analysed.  Any departures from the documentation plan defined in these standards should be scrutinised and discussed with project management.

### 5.2.3     Standards, practices, conventions and metrics

Adherence to all standards, practices and conventions should be monitored.

### 5.2.4     Reviews and audits

These Standards call for reviews of the URD, the SRD, the ADD, the DDD, the SVVP and the SCMP.  It also calls for the review and audit of the code during production. The review and audit arrangements described in the SVVP should be examined.  Many kinds of reviews are possible (e.g. technical, inspection and walkthrough). It should be verified that the review mechanisms appropriate for the type of project.  SQA personnel should participate in the review process.

### 5.2.5     Testing activities

Unit, integration, system and acceptance testing of executable software is essential to assure its quality.  Test plans, test designs,  test case, test procedures and test reports are described in the SVVP.  These should be reviewed by SQA personnel. They should monitor the testing activities carried out by the development team, test execution.  Additionally, other tests may be proposed in the SQAP.  These may be carried out by SQA personnel.

### 5.2.6     Problem reporting and corrective action

The problem handling procedure described in these standards is designed to report and track problems from identification until solution.  SQA personnel should monitor the execution of the procedures, described in the SCMP, and examine trends in problem occurrence.

### 5.2.7     Tools, techniques and methods

These Standards call for a tools, techniques and methods for software production to be defined at the project level. It is an SQA activity to check that appropriate tools, techniques and methods are selected and to monitor their correct application.

SQA personnel may decide that additional tools, techniques and methods are required to support their monitoring activity.  These should be described in the SQAP.

### 5.2.8     Code and media control

These Standards require that the procedures for the methods and facilities used to maintain, store, secure and document controlled versions of the identified software, be defined in the SCMP.  SQA personnel should check that appropriate procedures have been defined in the SCMP and carried out.

### 5.2.9     Supplier control

Software items acquired from external suppliers must always be checked against the standards for the project. An SQAP shall be produced by each contractor developing software.  An SQAP is not required for commercial software.

5.2.10    Records collection, maintenance and retention

These standards define a set of documents that must be produced in any project.  Additional documents, for example minutes of meetings and review records, may also be produced.  SQA personnel should check that appropriate methods and facilities are used to assemble, safeguard, and maintain all this documentation for at least the life of the project. Documentation control procedures are defined in the SCMP.

5.2.11    Training

SQA personnel should check that development staff are properly trained for their tasks and identify any training that is necessary.

Training plans are documented in the SPMP.

5.2.12    Risk management

All projects must identify the factors that are critical to their success and control these factors. This is called `risk management'. Project management must always analyse the risks that affect the project. Their findings are documented in the SPMP.  SQA personnel should monitor the risk management activity, and advise project management on the methods and procedures to identify, assess,and control areas of risk.

## 5.3       THE SOFTWARE QUALITY ASSURANCE PLAN

All software quality assurance activities shall be documented in the Software Quality Assurance Plan (SQAP). The recommended table  of contents for the SQAP is presented in Appendix C. This table of contents is derived from the IEEE Standard for Software Quality Assurance Plans (IEEE Std 730.1-1989).

## 5.4       EVOLUTION OF THE SQAP THROUGHOUT THE LIFE CYCLE

### 5.4.1     UR phase

By the end of the UR review, the SR phase section of the SQAP shall be produced (SQAP/SR). The SQAP/SR shall describe, in detail, the quality assurance activities to be carried out in the SR phase.

The SQAP/SR shall outline  the quality assurance plan for the rest of the project.

### 5.4.2     SR phase

During the SR phase, the AD phase section of the SQAP shall be produced (SQAP/AD). The SQAP/AD shall cover in detail all the quality assurance activities to be carried out in the AD phase.

In the SR phase, the SRD should be analysed to extract any constraints that relate to software quality assurance (e.g. standards and documentation requirements).

### 5.4.3     AD phase

During the AD phase, the DD phase section of the SQAP shall be produced (SQAP/DD). The SQAP/DD shall cover in detail all the quality assurance activities to be carried out in the DD phase.

### 5.4.4     DD phase

During the DD phase, the TR phase section of the SQAP shall be produced (SQAP/TR). The SQAP/TR shall cover in detail all the quality assurance activities to be carried out from the start the TR phase until final acceptance in the OM phase.

This page is intentionally left blank

# P a r t  3   A p p e n d i c e s

# APPENDIX A: GLOSSARY

## A.1       LIST OF TERMS

The terminology used in the ESA Software Engineering Standards conforms to ANSI/IEEE Std 729-1983, `IEEE Standard Glossary of Software Engineering Terminology'. This section contains definitions of terms:

- that are not contained in ANSI/IEEE Std 729-1983;

- that have multiple definitions in ANSI/IEEE Std 729-1983, one of which is used in these Standards (denoted by *);

- whose ISO definition is preferred (denoted by ISO and taken from ISO 2382, `Glossary of Terms used in Data Processing);

Component

General term for a part of a software system.  Components may be assembled and decomposed to form new components.  In the production phases, components are implemented as modules, tasks or programs, any of which may be configuration items.  This usage of the term is more general than in ANSI/IEEE parlance, which defines a component as a `basic part of a system or program'; in ESA PSS-05-0, components may not be `basic' as they can be decomposed.

Concurrent Production and Documentation

A technique of software development where the documentation of a module proceeds in parallel with its production, i.e. detailed design specifications, coding and testing.

------------------------

1 Copies of IEEE standards may be purchased (by credit card) from:

IEEE Service Center

455 Hoes lane, P.O. Box 1331,

Piscataway, NJ08855-1331, USA

Tel: 908-981-0060

2 Copies of ISO standards may be purchased (by credit card) from:

BSI Sales Dept,

Linfood Wood

Milton Keynes, MK14 6LE, U.K.

Tel: 0908-2211666

Decomposition

The breaking down into parts.

Software Development

The period from URD delivery to final acceptance, during which the   software is produced.

Developer

The person or organisation responsible for the developing the software from a specification of the user requirements to an operational system.

Environment

Either: Physical conditions such as temperature, humidity and cleanliness, within which a computer system operates; or, the support and utility software and hardware.

Formal Method

A mathematically precise means of specifying software, enabling specifications to be proven consistent.

Interface Control Document

A specification of an interface between a system and an external system.

Layer

One hierarchical level in the decomposition of a system.

Logical model

An implementation-independent representation of a real world process;  contrast physical model.

Model

A representation of a real world process. A software model is composed of symbols organised according to some convention.

Maintainability

The ease with which software can be maintained (*).

Nonconformance

A statement of conflict between descriptive documentation and the object described.

Physical model

An implementation-dependent representation of a real world process;    contrast logical model.

Product Assurance

The totality of activities, standards, controls and procedures in the lifetime of a product which establishes confidence that the delivered product will conform adequately to customer requirements (Product Assurance and Safety Policy and Basic Requirements for ESA Space Systems, ESA PSS-01-0, May 1990).

Production

The process of writing and testing software, as opposed to design and operations.

Project

Either the development process or the organisation devoted to the development process.

Prototype

An executable model of selected aspects of a proposed system.

Release

A baseline made available for use.

Reliability

The probability that software will not cause the failure of a system for a specified time under specified conditions.

Response Time

The elapsed time between the end of an inquiry or demand on a computer system and the beginning of the response (ISO).

Review

An activity to verify that the outputs of a phase in the software life cycle conform to their specifications (contrast IEEE: `Design Review'.)

Stability

Quality of not changing. Either in the short term, not breaking down, longer term, not subject to design and/or requirements changes (Contrast IEEE (1) the ability to continue unchanged despite disturbing or  disruptive events, (2) the ability to return to an original state after disturbing or disruptive events).

Software

The programs, procedures, rules and all associated documentation pertaining to the operation of a computerised system (ISO).

Task

A software component that executes sequentially.  A task may execute in parallel with other tasks.

Traceability

The ability to relate an input to a phase of the software life cycle to an output from that phase. The item may be software or documentation.

Traceability Matrix

Matrix showing which outputs correspond to which inputs. More often showing which parts of a design satisfy which requirements.

Trade-off

Comparison of alternatives to determine the optimal solution.

Turn-around

The elapsed time between submission of a job and the return of the complete output (ISO).

User

Any individual or group ultimately making use of the output from a computer system, distinct from personnel responsible for building, or maintaining the system.

Verification

The act of reviewing, inspecting, testing, checking, auditing, or otherwise establishing and documenting whether items, processes,or documents conform to specified requirements (*).

Version

A stage in the evolution of a configuration item.

Work-Around

A temporary solution to a problem.

Work Breakdown Structure

The WBS describes the hierarchy of tasks (grouped into `work packages') to be carried out in a project. The WBS corresponds to the structure of the work to be performed, and reflects the way in which the project costs will be summarised and reported.

Work Package

A detailed, short span, unit of work to be performed in a project.

## A.2       LIST OF ACRONYMS

AD    Architectural Design

ADD   Architectural Design Document

AD/R  Architectural Design Review

ANSI  American National Standards Institute

AT    Acceptance Test

BSSC  Board for Software Standardisation and Control

CASE  Computer Aided Software Engineering

DCR   Document Change Record

DD    Detailed Design and production

DDD   Detailed Design and production Document

DD/R  Detailed Design and production Review

DSS   Document Status Sheet

ESA   European Space Agency

IEEE  Institute of Electrical and Electronics Engineers

ISO   International Standards Organisation

ICD   Interface Control Document

IT    Integration Test

PA    Product Assurance

PHD   Project History Document

PSS   Procedures, Specifications and Standards

QA    Quality Assurance

RID   Review Item Discrepancy

SCM   Software Configuration Management

SCMP  Software Configuration Management Plan

SCR   Software Change Request

SPM   Software Project Management

SPMP  Software Project Management Plan

SMR   Software Modification Report

SPR   Software Problem Report

SQA   Software Quality Assurance

SQAP  Software Quality Assurance Plan

SR    Software Requirements

SRD   Software Requirements Document

SRN   Software Release Note

SR/R  Software Requirements Review

ST    System Test

STD   Software Transfer Document

SUM   Software User Manual

SVVP  Software Verification and Validation Plan

UR    User Requirements

URD   User Requirements Document

UR/R  User Requirements Review

UT    Unit Tests

# APPENDIX B   SOFTWARE PROJECT DOCUMENTS

This Appendix summarises the documents that can be produced in a software Engineering Project.  Table A1 summarises technical documents. Table A2 summarises the plans. Table A3 summarises reports, forms and  other documentation.

---------------------------------------------------------------------------------------------------------------------------------------

Acronym         	Name                          	Purpose

---------------------------------------------------------------------------------------------------------------------------------------

URD       	User Requirements       	To state the needs of the users of the Document   software system.

SRD       	Software Requirements   To specify the requirements of the software system from the developer's

point of view. The SRD incorporates the user requirements described in the Document URD.

ADD       	Architectural Design    	To specify the top-level components of the Document   software.  The

ADD fulfils the software  requirements stated in the SRD.

DDD       	Detailed Design   	To specify the bottom-level components  Document   of the software.  The

DDD fulfils the   requirements laid down in the SRD, following the top-

level design described   in the ADD.

SUM      	 Software User Manual    	To state what the software does and how to  operate the software.

STD       	Software Transfer       	To contain the checked configuration item  list and SPRs, SCRs, SMRs

generated in the  TR phase

PHD       	Project History         	To record significant information about  the specification, design,

production and   operation of the software.

------------------------------------------------------------------------------------------------------------------------------------------

Table A1 - Technical documents required by ESA PSS-05-0

-----------------------------------------------------------------------------------------------------------------------------

Acronym       	Name                           	Purpose

-----------------------------------------------------------------------------------------------------------------------------

SPMP      	Software Project        	To state the organisation, WBS, schedule  Management Plan  and budget,

for each development phase.

SCMP      	Software Configuration  	To state the procedures for the  Management Plan  identifying, controlling,

and recording  the status of software items.

SVVP      	Software Verification 	To state the procedures for testing the software and for verifying that the

and Validation Plan 	products of each phase are consistent with their inputs.

SQAP      	Software Quality        	To state the procedures for assuring the quality of the software products

Assurance Plan.

------------------------------------------------------------------------------------------------------------------------------------------

Table A2 - Plans required by ESA PSS-05-0

-----------------------------------------------------------------------------------------------------------------------------

Acronym       	Name                           		Purpose

-----------------------------------------------------------------------------------------------------------------------------

DCR       	Document Change Record  	To record a set of changes to a document.

DSS       	Document Status Sheet   		To summarise the issues and revisions of   a document.

RID       	Review Item Discrepancy 	To state issues to be addressed in a review and record decisions

made.

SCR       	Software Change Request 	To describe changes required in the software and its

documentation in the TR   and OM phases, including new

requirements.

SMR       	Software Modification   		To describe changes made to the software and its documentation

Report 				in the TR and OM  phases.

SPR       	Software Problem Report 		To record a problem reported in the use  or test of software and its

documentation.

SRN       	Software Release Note   		To summarise changes made to software with respect to the

previous release.

-------------------------------------------------------------------------------------------------------------------------------------

Table A3 - Reports and forms required by PSS-05-0

# APPENDIX C    DOCUMENT TEMPLATES

All documents should contain the following service information:

a - Abstract

b - Table of contents

c - Document Status Sheet

d - Document Change Records made since last issue

If there is no information pertinent to a section, the following appear below the section heading: `This section not applicable', with the appropriate reasons for this exclusion.

Comments on the tables of contents are enclosed in parentheses.

Section titles which are to be provided by document authors are enclosed in square brackets.

## APPENDIX C.1  URD table of contents

1         Introduction

1.1 Purpose

1.2 Scope

1.3 Definitions, acronyms and abbreviations

1.4 References

1.5 Overview

2         General Description

2.1 Product perspective

2.2 User characteristics

2.3 General constraints

2.4 Assumptions and dependencies

2.5 Operational environment

3         Specific Requirements

3.1   Capability requirements

3.2   Constraint requirements

## APPENDIX C.2  SRD table of contents

1         Introduction

1.1 Purpose

1.2 Scope

1.3 Definitions, acronyms and abbreviations

1.4 References

1.5 Overview

2         General Description

2.1 Relation to current projects

2.2 Relation to predecessor and successor projects

2.3 Function and purpose

2.4 Environmental considerations

2.5 Relation to other systems

2.6 General constraints

2.7 Model description

3         Specific Requirements

(The subsections may be regrouped around high-level functions)

3.1 Functional requirements

3.2 Performance requirements

3.3 Interface requirements

3.4 Operational requirements

3.5 Resource requirements

3.6 Verification requirements

3.7 Acceptance testing requirements

3.8 Documentation requirements

3.9 Security requirements

3.10 Portability requirements

3.11 Quality requirements

3.12 Reliability requirements

3.13 Maintainability requirements

3.14 Safety requirements

4         User Requirements vs Software Requirements Traceability matrix

## APPENDIX C.3  ADD table of contents

1         Introduction

1.1   Purpose

1.2   Scope

1.3   Definitions, acronyms and abbreviations

1.4   References

2         System Overview

3         System Context

3.n   External interface definition

4         System Design

4.1   Design method

4.2   Decomposition description

5         Component Description

5.n   Component identifier|

5.n.1 Type

5.n.2 Purpose

5.n.3 Function

5.n.4 Subordinates

5.n.5 Dependencies

5.n.6 Interfaces

5.n.7 Resources

5.n.8 References

5.n.9 Processing

5.n.10 Data

6         Feasibility and Resource Estimates

7         Software Requirements vs Components Traceability matrix

## APPENDIX C.4  DDD table of contents

Part 1 - General Description

1    Introduction

1.1   Purpose

1.2   Scope

1.3   Definitions, acronyms and abbreviations

1.4   References

1.5   Overview

2    Project Standards, Conventions and Procedures

2.1   Design standards

2.2   Documentation standards

2.3   Naming conventions (including files, programs, modules etc)

2.4   Programming standards

2.5   Software development tools

Part 2 - Component Design Specifications

n    Component identifier|

n.1   Identifier

n.2   Type

n.3   Purpose

n.4   Function

n.5   Subordinates

n.6   Dependencies

n.7   Interfaces

n.8   Resources

n.9   References

n.10  Processing

n.11  Data

Appendix A      Source code listings

Appendix B      Software Requirements vs Component Traceability matrix

## APPENDIX C.5  SUM table of contents

1         Introduction

1.1   Intended readership

1.2   Applicability statement

1.3   Purpose

1.4   How to use this document

1.5   Related documents (including applicable documents)

1.6   Conventions

1.7   Problem reporting instructions

2         Overview section|

(The section ought to give the user a general understanding of what

parts of software provide the capabilities needed)

3         Instruction section|

(For each operation, provide...

(a)   Functional description

(b)   Cautions and warnings

(c)   Procedures, including,

- Set-up and initialisation

- Input operations

- What results to expect

(d)   Probable errors and possible causes)

4         Reference section|

(Describe each operation, including:

(a)   Functional description

(b)   Cautions and warnings

(c)   Formal description, including as appropriate:

- required parameters

- optional parameters

- default options

- order and syntax

(d)   Examples

(e)   Possible error messages and causes

(f)   Cross references to other operations)

Appendix A      Error messages and recovery procedures

Appendix B      Glossary

Appendix C      Index (for manuals of 40 pages or more)

## APPENDIX C.6  STD table of contents

1         Introduction

1.1   Purpose

1.2   Scope

1.3   Definitions, acronyms and abbreviations

1.4   References

2         Installation Procedures

3         Build Procedures

4         Configuration Item List

5         Acceptance Test Report Summary

6         Software Problem Reports

7         Software Change Requests

8         Software Modification Reports

## APPENDIX C.7  PHD table of contents

1         Description of the project

2         Management of the project

2.1   Contractual approach (if applicable)

2.2   Project organisation

2.3   Methods used

2.4   Planning

3         Software Production

3.1   Estimated vs. actual amount of code produced

3.2   Documentation

3.3   Estimated vs. actual effort

3.4   Computer resources

3.5   Analysis of productivity factors

4         Quality Assurance Review

5         Financial Review

6         Conclusions

7         Performance of the system in OM phase

## APPENDIX C.8  SPMP table of contents

Software Project Management Plan for the SR Phase

1     Introduction

1.1   Project overview

1.2   Project deliverables

1.3   Evolution of the SPMP

1.4   Reference materials

1.5   Definitions and acronyms

2     Project Organisation

2.1   Process model

2.2   Organisational structure

2.3   Organisational boundaries and interfaces

2.4   Project responsibilities

3     Managerial process

3.1   Management objectives and priorities

3.2   Assumptions, dependencies and constraints

3.3   Risk management

3.4   Monitoring and controlling mechanisms

3.5   Staffing plan

4     Technical Process

4.1   Methods, tools and techniques

4.2   Software documentation

4.3   Project support functions

5     Work Packages, Schedule, and Budget

5.1   Work packages

5.2   Dependencies

5.3   Resource requirements

5.4   Budget and resource allocation

5.5   Schedule

Software Project Management Plan for the AD Phase   ----  Same

:

Software Project Management Plan for the DD Phase      :  structure as

:

Software Project Management Plan for the TR Phase   ----  SPMP/SR

## APPENDIX C.9  SCMP table of contents

Software Configuration Management Plan for the SR Phase

1     Introduction

1.1   Purpose

1.2   Scope

1.3   Glossary

1.4   References

2     Management

3     Configuration Identification

4     Configuration Control

4.1   Code control

4.2   Media control

4.3   Change control

5     Configuration Status Accounting

6     Tools, Techniques and Methods for SCM

7     Supplier Control

8     Records Collection and Retention

Software Configuration Management Plan for the AD Phase   ----  Same

:

Software Configuration Management Plan for the DD Phase      :  structure as

:

Software Configuration Management Plan for the TR Phase   ----  SCMP/SR

## APPENDIC C.10  SVVP table of contents

Software Verification and Validation Plan for the SR Phase

1     Purpose

2     Reference Documents

3     Definitions

4     Verification overview

4.1   Organisation

4.2   Master schedule

4.3   Resources summary

4.4   Responsibilities

4.5   Tools, techniques and methods

5     Verification Administrative Procedures

5.1   Anomaly reporting and resolution

5.2   Task iteration policy

5.3   Deviation policy

5.4   Control procedures

5.5   Standards, practices and conventions

6     Verification Activities

7.1   Traceability matrix template

7.2   Formal proofs

7.3   Reviews

7     Software Verification Reporting

Software Verification and Validation Plan for the AD Phase  ----  Same

:  structure as

Software Verification and Validation Plan for the DD Phase  ----  SVVP/SR

Acceptance Test Specification

1     Test Plan

1.1   Introduction

1.2   Test items

1.3   Features to be tested

1.4   Features not to be tested

1.5   Approach

1.6   Item pass/fail criteria

1.7   Suspension criteria and resumption requirements

1.8   Test deliverables

1.9   Testing tasks

1.10  Environmental needs

1.11  Responsibilities

1.12  Staffing and training needs

1.13  Schedule

1.14  Risks and contingencies

1.15  Approvals

2     Test Designs (for each test design...)

2.n.1 Test design identifier

2.n.2 Features to be tested

2.n.3 Approach refinements

2.n.4 Test case identification

2.n.5 Feature pass/fail criteria

3     Test Case Specifications (for each test case...)

3.n.1 Test case identifier

3.n.2 Test items

3.n.3 Input specifications

3.n.4 Output specifications

3.n.5 Environmental needs

3.n.6 Special procedural requirements

3.n.7 Intercase dependencies

4     Test Procedures (for each test case...)

4.n.1 Test procedure identifier

4.n.2 Purpose

4.n.3 Special requirements

4.n.4 Procedure steps

5     Test Reports (for each execution of a test procedure ...)

5.n.1 Test report identifier

5.n.2 Description

5.n.3 Activity and event entries

System Test Specification                ---  Same

Integration Test Specification             :  structure as

Unit Test Specification (may be in DDD)  ---  SVVP/AT

## APPENDIX C.11   SQAP table of contents

Software Quality Assurance Plan for the SR phase

1     Purpose

2     Reference Documents

3     Management

4     Documentation

5     Standards, practices, conventions and metrics

5.1   Documentation standards

5.2   Design standards

5.3   Coding standards

5.4   Commentary standards

5.5   Testing standards and practices

5.6   Selected software quality assurance metrics

5.7   Statement of how compliance is to be monitored

6     Review and audits

6.1   Purpose

6.2   Minimum requirements

7     Test

8     Problem reporting and corrective action

9     Tools, techniques and methods

10    Code control

11    Media control

12    Supplier control

13    Records collection, maintenance and retention

14    Training

15    Risk Management

16    Outline of the rest of the project

Software Quality Assurance Plan for the AD Phase     ----  Same

:

Software Quality Assurance Plan for the DD Phase        :  structure as

:

Software Quality Assurance Plan for the TR Phase     ----  SQAP/SR

# APPENDIX D   SUMMARY OF MANDATORY PRACTICES

These mandatory practices have been extracted for ease of reference, and can be used as a review checklist.  They are labelled with the chapter they come from, suffixed with a sequence number. This number corresponds to the order of the requirement in the chapter.

## APPENDIX D.1    SOFTWARE LIFE CYCLE

SLC01     The products of a software development project shall be delivered in a timely manner and be fit for their purpose.

SLC02     Software development activities shall be systematically planned and carried out.

SLC03     All software projects shall have a life cycle approach which includes the basic phases shown in Figure 1.2:

UR phase    -     Definition of the user requirements

SR phase    -     Definition of the software requirements

AD phase    -     Definition of the architectural design

DD phase    -     Detailed design and production of the code

TR phase    -     Transfer of the software to operations

OM phase    -     Operations and maintenance

## APPENDIX D.2    UR PHASE

UR01      The definition of the user requirements shall be the responsibility of the user.

UR02      Each user requirement shall include an identifier.

UR03      Essential user requirements shall be marked as such.

UR04      For incremental delivery, each user requirement shall include a measure of priority so that the developer can decide the production schedule.

UR05      The source of each user requirement shall be stated.

UR06      Each user requirement shall be verifiable.

UR07      The user shall describe the consequences of losses of availability, or breaches of security, so that developers can fully appreciate the criticality of each function.

UR08      The outputs of the UR phase shall be formally reviewed during the User Requirements Review.

UR09      Non-applicable user requirements shall be clearly flagged in the URD.

UR10      An output of the UR phase shall be the User Requirements Document (URD).

UR11      The URD shall always be produced before a software project is started.

UR12      The URD shall provide a general description of what the user expects the software to do.

UR13      All known user requirements shall be included in the URD.

UR14      The URD shall describe the operations the user wants to perform with the software system.

UR15      The URD shall define all the constraints that the user wishes to impose upon any solution.

UR16      The URD shall describe the external interfaces to the software system or reference them in ICDs that exist or are to be written.

## APPENDIX D.3    SR PHASE

SR01      SR phase activities shall be carried out according to the plans defined in the UR phase.

SR02      The developer shall construct an implementation-independent model of what is needed by the user.

SR04      Each software requirement shall include an identifier.

SR05      Essential software requirements shall be marked as such.

SR06      For incremental delivery, each software requirement shall include a measure of priority so that the developer can decide the production schedule.

SR07      References that trace software requirements back to the URD shall accompany each software requirement.

SR08      Each software requirement shall be verifiable.

SR09      The outputs of the SR phase shall be formally reviewed during the Software Requirements Review.

SR10      An output of the SR phase shall be the Software Requirements Document (SRD).

SR11      The SRD shall be complete.

SR12      The SRD shall cover all the requirements stated in the URD.

SR13      A table showing how user requirements correspond to software requirements shall be placed in the SRD.

SR14      The SRD shall be consistent.

SR15      The SRD shall not include implementation details or terminology, unless it has to be present as a constraint.

SR16      Descriptions of functions ... shall say what the software is to do, and must avoid saying how it is to be done.

SR17      The SRD shall avoid specifying the hardware or equipment, unless it is a constraint placed by the user.

SR18      The SRD shall be compiled according to the table of contents provide in Appendix C.

## APPENDIX D.4    AD PHASE

AD01      AD phase activities shall be carried out according to the plans defined in the SR phase.

AD02      A recognised method for software design shall be adopted and applied consistently in the AD phase.

AD03      The developer shall construct a `physical model', which describes

the design of the software using implementation terminology.

AD04      The method used to decompose the software into its component parts shall permit a top-down approach.

AD05      Only the selected design approach shall be reflected in the ADD.

For each component the following information shall be detailed in the ADD:

AD06                  data input;

AD07                  functions to be performed;

AD08                  data output.

AD09      Data structures that interface components shall be defined in the ADD.

Data structure definitions shall include the:

AD10                  description of each element (e.g. name, type, dimension);

AD11                  relationships between the elements (i.e. the structure);

AD12                  range of possible values of each element;

AD13                  initial values of each element.

AD14      The control flow between the components shall be defined in the ADD.

AD15      The computer resources (e.g. CPU speed, memory, storage, system software)  needed in the development environment and the operational environment shall be estimated in the AD phase and defined in the ADD.

AD16      The outputs of the AD phase shall be formally reviewed during the Architectural Design Review.

AD17      The ADD shall define the major components of the software and the interfaces between them.

AD18      The ADD shall define or reference all external interfaces.

AD19      The ADD shall be an output from the AD phase.

AD20      The ADD shall be complete, covering all the software requirements described in the SRD.

AD21      A table cross-referencing software requirements to parts of the  architectural design shall be placed in the

ADD.

AD22      The ADD shall be consistent.

AD23      The ADD shall be sufficiently detailed to allow the project leader to draw up a detailed implementation plan

and to control the overall project during the remaining development phases.

AD24      The ADD shall be compiled according to the table of contents provided in Appendix C.

## APPENDIX D.5    DD PHASE

DD01      DD phase activities shall be carried out according to the plans defined in the AD phase.

The detailed design and production of software shall be based on the following three principles:

DD02                  top-down decomposition;

DD03                  structured programming;

DD04                  concurrent production and documentation.

DD05      The integration process shall be controlled by the software configuration management procedures defined in

the SCMP.

DD06      Before a module can be accepted, every statement in a module shall be executed successfully at least once.

DD07      Integration testing shall check that all the data exchanged across an interface agrees with the data structure specifications in the ADD.

DD08      Integration testing shall confirm that the control flows defined in the ADD have been implemented.

DD09      System testing shall verify compliance with system objectives, as stated in the SRD.

DD10      When the design of a major component is finished, a critical design review shall be convened to certify its

readiness for implementation.

DD11      After production, the DD Review (DD/R) shall consider the results of the verification activities and decide

whether to transfer the software.

DD12      All deliverable code shall be identified in a configuration item list.

DD13      The DDD shall be an output of the DD phase.

DD14      Part 2 of the DDD shall have the same structure and identification scheme as the code itself, with a 1:1

correspondence between sections of the documentation and the software components.

DD15      The DDD shall be complete, accounting for all the software requirements in the SRD.

DD16      A table cross-referencing software requirements to the detailed design components shall be placed in the

DDD.

DD17      A Software User Manual (SUM) shall be an output of the DD phase.

## APPENDIX D.6    TR PHASE

TR01      Representatives of users and operations personnel shall participate in acceptance tests.

TR02      The Software Review Board (SRB) shall review the software's performance in the acceptance tests and

recommend, to the initiator, whether the software can be provisionally accepted or not.

TR03      TR phase activities shall be carried out according to the plans defined in the DD phase.

TR04      The capability of building the system from the components that are directly modifiable by the maintenance team shall be established.

TR05      Acceptance tests necessary for provisional acceptance shall be indicated in the SVVP.

TR06      The statement of provisional acceptance shall be produced by the initiator, on behalf of the users, and sent to the developer.

TR07      The provisionally accepted software system shall consist of the outputs of all previous phases and modifications found necessary in the TR phase.

TR08      An output of the TR phase shall be the STD.

TR09      The STD shall be handed over from the developer to the maintenance organisation at provisional acceptance.

TR10      The STD shall contain the summary of the acceptance test reports,ocumentation about software changes performed during the TR phase.

## APPENDIX D.7    OM PHASE

OM01      Until final acceptance, OM phase activities that involve the developer shall be carried out according to the plans defined in the SPMP/TR.

OM02      All the acceptance tests shall have been successfully completed before the software is finally accepted.

OM03      Even when no contractor is involved, there shall be a final acceptance milestone to arrange the formal hand-over from software development to maintenance.

OM04      A maintenance organisation shall be designated for every software product in operational use.

OM05      Procedures for software modification shall be defined.

OM06      Consistency between code and documentation shall be maintained.

OM07      Resources shall be assigned to a product's maintenance until it is retired.

OM08      The SRB ... shall authorise all modifications to the software.

OM09      The statement of final acceptance shall be produced by the initiator, on behalf of the users, and sent to the developer.

OM10      The PHD shall be delivered to the initiator after final acceptance.

## APPENDIX D.8    SOFTWARE PROJECT MANAGEMENT

SPM01     All software project management activities shall be documented in the Software Project Management Plan

(SPMP).

SPM02     By the end of the UR review, the SR phase section of the SPMP shall be produced (SPMP/SR).

SPM03     The SPMP/SR shall outline a plan for the whole project.

SPM04     A precise estimate of the effort involved in the SR phase shall be included in the SPMP/SR.

SPM05     During the SR phase, the AD phase section of the SPMP shall be produced (SPMP/AD).

SPM06     An estimate of the total project cost shall be included in the SPMP/AD.

SPM07     A precise estimate of the effort involved in the AD phase shall be included in the SPMP/AD.

SPM08     During the AD phase, the DD phase section of the SPMP shall be produced (SPMP/DD).

SPM09     An estimate of the total project cost shall be included in the SPMP/DD.

SPM10     The SPMP/DD shall contain a WBS that is directly related to the decomposition of the software into

components.

SPM11     The SPMP/DD shall contain a planning network showing relationships of coding, integration and testing

activities.

SPM12     No software production work packages in the SPMP/DD shall last longer than 1 man-month.

SPM13     During the DD phase, the TR phase section of the SPMP shall be produced (SPMP/TR).

## APPENDIX D.9    SOFTWARE CONFIGURATION MANAGEMENT

SCM01     All software items, for example documentation, source code, object or relocatable code, executable code, files, tools, test software and data, shall be subjected to configuration management procedures.

SCM02     The configuration management procedures shall establish methods for identifying, storing and changing software items through development, integration and transfer.

SCM03     A common set of configuration management procedures shall be used.

Every configuration item shall have an identifier that distinguishes it from other items with different:

SCM04                 requirements, especially functionality and interfaces;

SCM05                 implementation.

SCM06     Each component defined in the design process shall be designated as a CI and include an identifier.

SCM07     The identifier shall include a number or a name related to the purpose of the CI.

SCM08     The identifier shall include an indication of the type of processing the CI is intended for (e.g. filetype

information).

SCM09     The identifier of a CI shall include a version number.

SCM10     The identifier of documents shall include an issue number and a revision number.

SCM11     The configuration identification method shall be capable of accommodating new CIs, without requiring the modification of the identifiers of any existing CIs.

SCM12     In the TR phase, a list of configuration items in the first release shall be included in the STD.

SCM13     In the OM phase, a list of changed configuration items shall be included in each Software Release Note

(SRN).

SCM14     An SRN shall accompany each release made in the OM phase.

As part of the configuration identification method, a software module shall have a standard header that includes:

SCM15                 configuration item identifier (name, type, version);

SCM16                 original author;

SCM17                 creation date;

SCM18                 change history (version/date/author/description).

All documentation and storage media shall be clearly labelled in a standard format, with at least the following data:

SCM19                 project name;

SCM20                 configuration item identifier (name, type, version);

SCM21                 date;

SCM22                 content description.

To ensure security and control of the software, at a minimum, the following software libraries shall be implemented for storing all the deliverable components (e.g. documentation, source and executable code, test files, command procedures):

SCM23                 Development (or Dynamic) library;

SCM24                 Master (or Controlled) library;

SCM25                 Static (or Archive) library.

SCM26     Static libraries shall not be modified.

SCM27     Up-to-date security copies of master and static libraries shall always be available.

SCM28     Procedures for the regular backup of development libraries shall be established.

SCM29     The change procedure described (in Part 2, Section 3.2.3.2.1)  shall be observed when changes are needed to a delivered document.

SCM30     Software problems and change proposals shall be handled by the procedure described (in Part 2, Section

3.2.3.2).

SCM31     The status of all configuration items shall be recorded.

To perform software status accounting, each software project shall record:

SCM32                 the date and version/issue of each baseline;

SCM33                 the date and revision number of each document change;

SCM34                 the date and status of each SPR, SCR and SMR;

SCM35                 a summary description of each Configuration Item.

SCM36     As a minimum, the SRN shall record the faults that have been repaired and the new requirements that have been incorporated.

SCM37     For each release, documentation and code shall be consistent.

SCM38     Old releases  shall be retained, for reference.

SCM39     Modified software shall be retested before release.

SCM40     All software configuration management activities shall be documented in the Software Configuration Management Plan (SCMP).

SCM41     Configuration management procedures shall be in place before the production of software (code and documentation) starts.

SCM42     By the end of the UR review, the SR phase section of the SCMP shall be produced (SCMP/SR).

SCM43     The SCMP/SR shall cover the configuration management procedures for documentation, and any CASE tool outputs or prototype code, to be produced in the SR phase.

SCM44     During the SR phase, the AD phase section of the SCMP shall be produced (SCMP/AD).

SCM45     The SCMP/AD shall cover the configuration management procedures for documentation, and CASE tool outputs or prototype code, to be produced in the AD phase.

SCM46     During the AD phase, the DD phase section of the SCMP shall be produced (SCMP/DD).

SCM47     The SCMP/DD shall cover the configuration management procedures for documentation, deliverable code, and any CASE tool outputs or prototype code, to be produced in the  DD phase.

SCM48     During the DD phase, the TR phase section of the SCMP shall be produced (SCMP/TR).  The SCMP/TR shall cover the procedures for the configuration management of the deliverables in the operational environment.

## APPENDIX D.10   SOFTWARE VERIFICATION AND VALIDATION

SVV01     Forwards traceability requires that each input to a phase shall be traceable to an output of that phase.

SVV02     Backwards traceability requires that each output of a phase shall be traceable to an input to that phase.

SVV03     Functional  and physical audits shall be performed before the release of the software.

SVV04     All software verification and validation activities shall be documented in the Software Verification and Validation Plan (SVVP).

The SVVP shall ensure that the verification activities:

SVV05                 are appropriate for the degree of criticality of the  software;

SVV06                 meet the verification and acceptance testing requirements  (stated in the SRD);

SVV07                 verify that the product will meet the quality,   reliability, maintainability and safety requirements

(stated in the SRD);

SVV08                 are sufficient to assure the quality of the product.

SVV09     By the end of the UR review, the SR phase section of the SVVP shall be produced (SVVP/SR).

SVV10     The SVVP/SR shall define how to trace user requirements to software requirements, so that each software requirement can be justified.

SVV11     The developer shall construct an acceptance test plan in the UR phase and document it in the SVVP.

SVV12     During the SR phase, the AD phase section of the SVVP shall be produced (SVVP/AD).

SVV13     The SVVP/AD shall define how to trace software requirements to components, so that each software component can be justified.

SVV14     The developer shall construct a system test plan in the SR phase and document it in the SVVP.

SVV15     During the AD phase, the DD phase section of the SVVP shall be produced (SVVP/DD).

SVV16     The SVVP/AD shall describe how the DDD and code are to be evaluated by defining the review and traceability procedures.

SVV17     The developer shall construct an integration test plan in the AD phase and document it in the SVVP.

SVV18     The developer shall construct a unit test plan in the DD phase and document it in the SVVP.

SVV19     The unit, integration, system and acceptance test designs shall be described in the SVVP.

SVV20     The unit integration, system and acceptance test cases shall be described in the SVVP.

SVV21     The unit, integration, system and acceptance test procedures shall be described in the SVVP.

SVV22     The unit, integration, system and acceptance test reports shall be described in the SVVP.

## APPENDIX D.11   SOFTWARE QUALITY ASSURANCE

SQA01     An SQAP shall be produced by each contractor developing software.

SQA02     All software quality assurance activities shall be documented in the Software Quality Assurance Plan

(SQAP).

SQA03     By the end of the UR review, the SR phase section of the SQAP shall be produced (SQAP/SR).

SQA04     The SQAP/SR shall describe, in detail, the quality assurance activities to be carried out in the SR phase.

SQA05     The SQAP/SR shall outline  the quality assurance plan for the rest of the project.

SQA06     During the SR phase, the AD phase section of the SQAP shall be produced (SQAP/AD).

SQA07     The SQAP/AD shall cover in detail all the quality assurance activities to be carried out in the AD phase.

SQA08     During the AD phase, the DD phase section of the SQAP shall be produced (SQAP/DD).

SQA09     The SQAP/DD shall cover in detail all the quality assurance activities to be carried out in the DD phase.

SQA10     During the DD phase, the TR phase section of the SQAP shall be produced (SQAP/TR).

SQA11     The SQAP/TR shall cover in detail all the quality assurance activities to be carried out from the start the TR phase until final acceptance in the OM phase.

## APPENDIX E  FORM TEMPLATES

Template forms are provided for:

DCR       -     	Document Change Record

DSS       -     	Document Status Sheet

RID       -     	Review Item Discrepancy

SCR       -     	Software Change Request

SMR       -     	Software Modification Report

SPR       -     	Software Problem Report

SRN       -     	Software Release Note

| DOCUMENT CHANGE RECORD | DCR Nº: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
|  | APPROVED BY: |  |
| 1. DOCUMENT TITLE: |  |  |
| 2. DOCUMENT REFERENCE NUMBER: |  |  |
| 3. DOCUMENT ISSUE/REVISION NUMBER: |  |  |
| 4. PAGE : 5. PARAGRAPH : 6. REASON FOR CHANGE |  |  |

| DOCUMENT STATUS SHEET |  |  |  |
| --- | --- | --- | --- |
| 1. DOCUMENT TITLE: |  |  |  |
| 2. DOCUMENT REFERENCE NUMBER: |  |  |  |
| 3. ISSUE | 4. REVISION | 5. DATE | 6. REASON FOR CHANGE |

| REVIEW ITEM DISCREPANCY | RID Nº: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
| - DOCUMENT TITLE: |  |  |
| - DOCUMENT REFERENCE NUMBER: |  |  |
| - DOCUMENT ISSUE/REVISION NUMBER: |  |  |
| - PROBLEM LOCATION: |  |  |
| - PROBLEM DESCRIPTION: |  |  |
| - RECOMMENDED SOLUTION: |  |  |
| - AUTHOR'S RESPONSE: |  |  |
| - REVIEW DECISION: CLOSE/UPDATE NEEDED/ACTION (underline choice) |  |  |

| SOFTWARE CHANGE REQUEST | SCR Nº: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
|  | RELATED SPRs: |  |
| 1. SOFTWARE ITEM TITLE: |  |  |
| 2. SOFTWARE ITEM VERSION / RELEASE NUMBER: |  |  |
| 3. PRIORITY: CRITICAL/URGENT/ROUTINE (underline choice): |  |  |
| 4. CHANGES REQUIRED: |  |  |
| 5. RESPONSIBLE STAFF: |  |  |
| 6. ESTIMATED START DATE, END DATE AND MANPOWER EFFORT: |  |  |
| 7. ATTACHMENTS: |  |  |

| SOFTWARE MODIFICATION REPORT | SRN NO: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
|  | RELATED SCRs: |  |
| - SOFTWARE ITEM TITLE: |  |  |
| - SOFTWARE ITEM VERSION/RELEASE NUMBER: |  |  |
| - CHANGES IMPLEMENTED: |  |  |
| - ACTUAL START DATE, END DATE AND MANPOWER EFFORT:: |  |  |
| 5. ATTACHMENTS Source Code | (tick as appropriate) |  |
| Test Procedures |  |  |
| Test Data |  |  |
| Test Results |  |  |
| Documentation Updates |  |  |

| SOFTWARE PROBLEM REPORT | SPR Nº: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
| - SOFTWARE ITEM TITLE: |  |  |
| - SOFTWARE ITEM VERSION/RELEASE NUMBER: |  |  |
| - PRIORITY: CRITICAL/URGENT/ROUTINE (underline choice) |  |  |
| - PROBLEM DESCRIPTION: |  |  |
| - DESCRIPTION OF ENVIRONMENT: |  |  |
| - RECOMMENDED SOLUTION: |  |  |
| - SOFTWARE REVIEW BOARD DECISION: |  |  |
| - ATTACHMENTS: |  |  |

| SOFTWARE RELEASE NOTE | SRN NO: |  |
| --- | --- | --- |
|  | DATE: |  |
|  | ORIGINATOR: |  |
|  | APPROVED BY: |  |
| - SOFTWARE ITEM TITLE: |  |  |
| - SOFTWARE ITEM VERSION/RELEASE NUMBER: |  |  |
| - CHANGES IN THIS RELEASE: |  |  |
| - CONFIGURATION ITEMS INCLUDED IN THIS RELEASE: |  |  |
| - 5. INSTALLATION INSTRUCTIONS: |  |  |

# Figures

# Apendix Index

abstraction, 1-31                      configuration item

acceptance test                         see Cl

case, 1-48                            configuration management

chanqe authority, 2-15                 see SCM

participation, 1-49                   configuration status accounting, 2-17

plan, 2-28                            constraint requirement, 1-15

practice for, 1-44                    control flow, 1-34

purpose, 1-50                         cost estimating

quality assurance of, 2-32             see estimating

requirement, 1-23                     costmodel, 2-7

requirements, 2-29                    coupling, 1-32

result, 1-51                          criticality, 1-15, 2-28

AD/R, 1-29, 1-35                       cross-reference matrix, 2-24

AD phase, 1-5, 1-29

adaptability requirement, 1-15         data structure, 1-34

ADD, 1-6, 1-29, 1-36                   DCR, 2-16, 2-18

ANSI                                   DD/R, 1- 39, 1-46

see IEEE                              DD phase, 1-6, 1-39

architectural design, 1-29             DDD, 1-6, 1-46

lowest level, 1-31                    debugger, 1-44

phase, 1-29                           decomposition, 1-20

specification of, 1-33                 functional, 1-31

audit, 2-27                             of components, 1-31

see functional audit                   system, xi

see physical audit                     top-down approach, 1-31

quality assurance of, 2-32            defect

availability requirement, 1-15          trend, 1-45

validation of, 1-7                    design quality criteria, 1-32

detailed design, 1-40

backup, 2-14                            phase, 1-39

baseline, 2-14, 2-18                   documentation

as a Cl, 2-12                          quality assurance of, 2-34

block diagram                           requirement, 1-24

AD phase, 1-33                        documentation plan

SR phase, 1-23                         quality-assurance of, 2-32

UR phase, 1-14                        DSS, 2-16

budgeting, 2-6

embedded system, 1-45

capability requirement, 1-15           estimating, 2-6

CASE tool                               AD phase, 2-10

AD phase, 1-30                         for future projects, 1-56

DD phase, 1-41                         SR phase, 2-9

SCM of, 2-19                           UR phase, 2-8

SR phase, 1-21                        evolutionary development, 1-10

change control                         external interface, 1-14, 2-9

documentation, 2-16                    change control, 2-15

general, 2-15                          in AD phase, 1-34

levels of, 2-15                        in SR phase, 1-23

procedures, 2-16                       in UR phase, 1-17

checkout, 1-49

Cl, 2-11                               feasibility, 1-14

identification, 2-12                  final acceptance, 1-7, 1-54

list, 1-50                             responsibility, 1-54

code, 1-41, 1-46                       formal method

control, 2-33                          for verification, 2-25

convention, 1-41                       SR phase, 1-27

documentation, 1-42                   formal proof, 2-25

production, 1-41                      formal review, 2-16

cohesion, 1-32                          see review

component, 1-34                        functional audit, 2-27

function of, 1-34                     functional requirement, 1-22

interface to, 1-34

computer resource, 1-35                handover, 1-49

computer virus, 1-24

HCl, 1-15                               use in inspection,2-24

module

ICD                                     acceptability, 1-43

AD phase, 1-34                         definition, 1-41

SR phase, 1-23                         header, 1-42, 2-13

UR phase, 1-14                         integration, 1-43

IEEE, viii                             MTTF, 1-24

Std 1012, 2-28                        MTTR, 1-24

Std 1016, 1-36

Std 1028, 2-23                        non-functional requirement, 1-31

Std 1042, 2-19

Std 1058, 1, 2-5                      OM phase, 1-7, 1-53

Std 1063, 1-47                        operational environment, 1-14

Std 729, 2-21, 3-A1                    acceptance test, 1-50

Std 73O 1, 2-31, 2-34                 operationalrequirement, 1-23

Std 828, 2-19                         operations phase, 1-53

Std 829, 2-28

Std 830, 1-28                         PA

implementation, 1-39                    see SQA

incremental delivery, 1-9              partitioning, 1-31

information hiding, 1-31, 1-40         password, 1-24

inspection, 2-24                       performance requirement, 1-22

installation, 1-49                     phase, 1-3

integration, 1-43                      physical audit, 2-27

integration test                       physical model, 1-30

see also test                         PHD, 1-7, 1-56

plan, 2-29                             AD phase, 1-33

purpose, 1-44                         planning, 2-6

integrity, 1-24                         network, 2-10

interface requirement, 1-22            portability requirement, 1-15, 1-24

interview, 1-14                        problem category, 2-17

problem reporting, 2-16

library, 2-14                           quality assurance of, 2-33

archive, 2-14                         product assurance

controlled, 2-14                       see SQA

development, 2-14                     production

dynamic, 2-14                          of code, 1-41

master, 2-14                           phase, 1-39

static, 2-14                          programming language, 1-35

life cycle, 1-3                        progress reporting, 2-8

milestone, 1-4                        project management, 2-5

verification, 2-21                    prototype, 2-9

logical model, 1-20                    prototyping, 1-11

in AD phase, 1-33

maintainability requirement, 1-24       in SR phase, 1-20

maintenance, 1-54                       in UR phase, 1-14

phase, 1-53                           provisional acceptance, 1-7

purpose, 1-53                          definition, 1-50

media                                  PS3-01-21, ix, 2-4, 2-31

control, 2-33

label, 2-14                           quality assurance

media control, 2-14                     see SQA

method                                 quality requirement, 1-24

for design, 1-30

quality assurance of, 2-33            regression testing, 1-55, 2-19

selection, 2-6                         in OM phase, 1-55

metric                                 release, 2-18

complexity, x                         reliability requirement, 1-24

data collection, 1-7                  requirement

design quality. 1-32                   see user requirement

for specifying requirements, 1-24      capture, 1-13

quality assurance of, 2-32             change in OM phase, 1-55

tools for, 1-7                         changing a, 1-12

see software requirement, 1-19        SPR, 2-17, 2-18

resource requirement, 1-23             SDA, 2-31

review                                 SGlAP

see inspection                         AD phase, 1-28, 2-34

see technical review                   DD phase, 1-37, 2-35

see walkthrough                        mandatory requirements, 2-34

AD/R, 1-35                             SR phase, 1-18, 2-34

DD/R, 1-45                             TR phase, 1-48, 2-35

module-level, 1-41                    SR/R, 1-19, 1-26

quality assurance of, 2-32            SR phase, 1-5, 1-19

SR/R, 1-26                            SRB, 1-49

types of, 2-23                         role in maintenance, 1-54

UR/R, 1-16                             SPR handling, 2-17

RlD, 2-16, 2-18                        SRD, 1-5, 1-19, 1-27

risk analysis, 2-6                      language, 1-27

risk management, 2-6                   SRN, 2-18

quality assurance of, 2-34             baseline release, 2-13

static analysis, 1-42

safety-critical, 1-27                  STD, 1-7, 1-51, 2-18

safety requirement, 1-25               structured english, 1-27

scheduling, 2-6                        structured programming, 1-40, 1-42

SCM ,2-11                              SUM, 1-6, 1-47

in integration, 1-43                  supplier control, 2-33

in OM phase, 1-55                     survey, 1-14

quality assurance of, 2-33            SVVP, 2-28

tool, 2-11                             acceptance tests, 1-17, 1-48

SCMP, 2-19                              AD phase, 1-28, 2-29

AD phase, 1-28, 2-19                   DD phase, 1-37, 2-29

DD phase, 1-37, 2-20                   integration tests, 1-37, 1-44

SR phase, 1-17, 2-19                   SR phase, 1-18, 2-28

TR phase, 1-48, 2-20                   system tests, 1-28, 1-45

SCR, 2-17, 2-18                         unit tests, 1-44

security requirement, 1-15, 1-24        UR phase, 2-28

simulator, 1-45                        system test

SMR, 2-17, 2-18                         see also test

Software Configuration Management       plan, 2-29

see SCM                                purpose, 1-44

software inspection

see inspection                        tailoring, x

software project management            technical

see SPM                                management, 2-6

software requirement                    review, 2-23

ambiguity, 1-25                       test

attributes of, 1-25                    see also acceptance test

classification, 1-22                   see also integration test

completeness, 1-25                     see also system test

consistency, 1-26                      see also unit test

definition phase, 1-19                 black box, 1-43

duplication, 1-26                      coverage, 1-44

identifler, 1-25                       in DD phase, 1-48

need, 1-25                             quality assurance of, 2-32

priority, 1-25                         types of, 2-25

source, 1-25                           white box, 1-43

specification, 1-21                   tool

stability, 1-25                        see also CASE tool

verifiability, 1-25                    for project planning, 2-10

SPM, 2-5                                needfor, 1-12

quality assurance of, 2-32             quality assurance of, 2-33

SPMP, 2-8                              top-down, 1-31, 1-40

AD phase, 1-5, 1-28, 2-9               decomposition, 1-20

DD phase, 1-6, 1-37, 2-10              design, 1-31

SR phase, 1-5, 1-17, 2-8               integration, 1-43

TR phase, 1-48, 2-10                  TR phase, 1-7, 1-49

traceability

backwards, 1-27, 2-24

forwards, 1-27,2-24

trade-off, 1-33

training, 1-53, 2-6, 2-34

transfer phase, 1-49

unittest,1-43

see also test

plan, 2-29

UR/R, 1-13, 1-16

UR phase, 1-5, 1-13

URD, 1-5, 1-13, 1-17

user requirement

ambiguity, 1-16

attributes of, 1-15

classification, 1-14

definition phase, 1-13

identifier, 1-15

need, 1-15

priority, 1-15

source, 1-16

specification, 1-14

stability, 1-16

verifiability, 1-16

validation, 2-21

verification, 2-21

verification requirement, 1-23

virus

see computer virus

walkthrough, 2-24

waterfall, 1-8

WBS, 2-7

Work-around, 1-55

Work Breakdown Structure

see WBS